## Sheet1
Audit Para Upload
Audit Ref. No. | SMART/2024-25/Ext/0150 DIUWAR
Bill No | Bill Date (yyyy-MM-dd) | PFMS No. | Para No. | Audit Category (Monetary/Non-Monetary) | Audit Section (Procurement/Technical/Finance/MIS/Others) | Audit Para Title | Audit Description | Severity (Critical/High/Medium/Low) | Para Amount (in Rs.)
NA | 2025-03-31 | NA | 4 | Non-Monetary | Procurement | Delay In Documentation | we observed that the Audit of the supply of 6,000 cotton picking bags to DIU Wardha under the contract dated 25.10.2024 with M/s Prakash Agro Plast revealed multiple non-compliances. Required documents under GCC Clause 13.1, including invoices, delivery notes, insurance certificate, warranty, and inspection certificates, were not submitted, resulting in contractual non-compliance. Delivery was due by 24.11.2024, but documents were still pending as of 14.07.2025. No Acceptance Certificate was issued under GCC Clause 16.1, yet payment was released despite incomplete documentation. Delivery records lacked transit and vehicle details, and the e-way bill was not submitted. ICAR testing indicated GSM of 160.3 against the required 200–250 GSM, and remedial action, including replacement of defective bags, was not taken by the supplier as mandated under GCC Clauses 28.5 and 28.6. Despite repeated requests from DIU and PIU, the defective goods were neither replaced nor collected, highlighting delays, quality deviations, and non-compliance with contractual obligations. | High | 1638000