## AuditPara
Audit Para Upload
Audit Ref. No. | SMART/2024-25/Ext/0150 DIUWAR
Bill No | Bill Date (yyyy-MM-dd) | PFMS No. | Para No. | Audit Category (Monetary/Non-Monetary) | Audit Section (Procurement/Technical/Finance/MIS/Others) | Audit Para Title | Audit Description | Severity (Critical/High/Medium/Low) | Para Amount (in Rs.)
NA | 2025-03-31 | NA | 1 | Non-Monetary | Others | Non-submission of documentation | It was observed that the PT return for the period April 2024 to March 2025 has not been filed. Hence, an amount of ₹1,000 should be recovered from the concerned person. (kindly refer Annexure 1) | High | 0
NA | 2025-03-31 | NA | 2 | Non-Monetary | Others | Delay In payement | It was observed that the GST for the month of July 2024, amounting to Rs. 7,621/-, was deposited with a delay of 30 days. | High | 0
124 | 2025-03-15 | C0525232265289 | 3 | Monetary | Procurement | Delay In Documentation | we observed that the Audit of the supply of 3,400 cotton storage bags to DIU Wardha under the contract dated 25.10.2024 with M/s Maa Bhagwati Biotech & Chemical revealed several non-compliances. Mandatory documents under GCC Clause 13.1, including warranty certificate, inspection certificate, and transit insurance policy, were not submitted, resulting in contractual non-compliance. Delivery memo lacked verification of technical specifications, transit details, and e-way bill. Samples were sent to Superintendence Company of India Pvt. Ltd., Mumbai, but the laboratory’s ISO certification and authorization for textile testing were not verified, and test results were significantly delayed (received 24.01.2025), hampering timely preventive action. Delivery was completed after the stipulated deadline of 24.11.2024, though liquidated damages of Rs. 52,479 were deducted. Despite this, required documents were still not submitted to the consignee, highlighting delays in testing, documentation gaps, and non-compliance with contractual obligations, warranting action by higher authorities. Date of payment 19.05.2025 of Rs.3498600 | High | 3498600
NA | 2025-03-31 | NA | 4 | Non-Monetary | Procurement | Delay In Documentation | we observed that the Audit of the supply of 6,000 cotton picking bags to DIU Wardha under the contract dated 25.10.2024 with M/s Prakash Agro Plast revealed multiple non-compliances. Required documents under GCC Clause 13.1, including invoices, delivery notes, insurance certificate, warranty, and inspection certificates, were not submitted, resulting in contractual non-compliance. Delivery was due by 24.11.2024, but documents were still pending as of 14.07.2025. No Acceptance Certificate was issued under GCC Clause 16.1, yet payment was released despite incomplete documentation. Delivery records lacked transit and vehicle details, and the e-way bill was not submitted. ICAR testing indicated GSM of 160.3 against the required 200–250 GSM, and remedial action, including replacement of defective bags, was not taken by the supplier as mandated under GCC Clauses 28.5 and 28.6. Despite repeated requests from DIU and PIU, the defective goods were neither replaced nor collected, highlighting delays, quality deviations, and non-compliance with contractual obligations. | High | 1638000