## AuditPara
Audit Para Upload
Audit Ref. No. | SMART/2024-25/Ext/0300 PIUDM
Bill No | Bill Date (yyyy-MM-dd) | PFMS No. | Para No. | Audit Category (Monetary/Non-Monetary) | Audit Section (Procurement/Technical/Finance/MIS/Others) | Audit Para Title | Audit Description | Severity (Critical/High/Medium/Low) | Para Amount (in Rs.)
AFCEINV2024069 | 2024-03-13 | C042401438878 | 1 | Monetary | Procurement | Irregularities in Payment and documentation | We noticed that payment has been made to AFC India Pvt ltd for consultancy payment for call Centre and help desk –Inception Report but following irregularities were noticed Tender cost – RS 34,872,10.40 a) As per agreement dated 12.02.2024 work to be completed within 4 month and the same has not been completed and extension has been given for 2 month for the period of 19.06.2024 to 19.08.2024 but work is not further in process or any of the ahead. The project work does not carried as per the deliverables b) Minute of the meeting for extension should be 19.06.2024 to 19.08.2024 but it is mentioned as 19.06.2024 to 19.09.2024 c) Team mobilization , discussing and requirement gathering monthly report is not available for audit verification d) Analysis and assessment stakeholder , interaction conducting requirement study monthly report is not available for audit verification First stage - subject of Office note sheet dated 22.03.2024 is revised inception report however submission date of inception report is not mentioned Second stage ( RFP / DPR and phase completion report ) - Subject to Office note sheet dated 25.06.2024 is for approval of revised DPR/ and revised estimate cost for establishment call centre and Redressal solution through a managed service for DOM however Hard copy received 01.05.2024 and online email copy received on 22.04.2024. Also, additionally Revised Report was received on 21.05.2024 and Revised RFP on 09.09.2024 date of payment 03.04.2024/ 20.06.2024 of Rs.1253031 | High | 1253031
AFCEIN2425008 | 2024-04-30 | C062417617829
NA | 2025-03-31 | C052429021462 | 2 | Monetary | Procurement | Delay in payment | at a delay of 06 months c) As per Mou dated 30.01.2024, Deliverable no 3 Develop Training module for officer of department before 31.03.2024 but Deliverable 2 was submitted on 14.10.2024 at a delay of 07 months d) As per Mou dated 30.01.2024, Deliverable no 4 Training of -50 master trainee to be done before 31.03.2024 but it held on in November 2024 at a delay of 8 months e) As per Mou dated 30.01.2024, Deliverable no 5 Designated and printed training resource material to be done before 31.03.2024 but it is not submitted f) As per Mou dated 30.01.2024, Deliverable no 6 training for 400 departmental field officer to be held before Nov 2024 but 3rd amendment was made on dated 06.02.2025 with a time extension till MAR 25. However, amendment in the extension was given after the actual deliverable period was ended g) As per MOU dated 30.01.2024, Deliverable no 7 training for 1200 APMC staff to be held before December 2024 but 3rd amendment was made on dated 06.02.2025 with a time extension till April 25. However, amendment in the extension was given after the actual deliverable period was ended h) As per Mou dated 30.01.2024, Deliverable no 8exposure visit for 1200 APMC staff to be held before Dec 2024 but3rd amendment was made on dated 06.02.2025 with a time extension till April 25. However, amendment in the extension was given after the actual deliverable period was ended i) As per Mou dated 30.01.2024, Deliverable no 9 assessed the impact pf training through online assessment prepare and submit the assessment / evaluation report before 30.01.2025 but 3rd amendment was made on dated 06.02.2025 with a time extension till August 25. However, amendment in the extension was given after the actual deliverable period was ended | High | 11940913
NA | 2025-03-31 | NA | 3 | Monetary | Procurement | Delay in payment | We observed that payment has been made to KPMG for providing consultancy services for technical cell of PIU DOM however following irregularities were noticed | High | 2852544