## AuditPara
Audit Para Upload
Audit Ref. No. | SMART/2022-23/Ext/0120 DIUAU
Bill No | Bill Date (yyyy-MM-dd) | PFMS No. | Para No. | Audit Category (Monetary/Non-Monetary) | Audit Section (Procurement/Technical/Finance/MIS/Others) | Audit Para Title | Audit Description | Severity (Critical/High/Medium/Low) | Para Amount (in Rs.)
1 | 2023-03-31 | DIUAurangabad1 | 1 | Non-Monetary | Procurement | Training Exposure Visit – Within & Outside State Chaitanya Tours & Travels | • Payment to Chaitanya Tours & Travels of Rs. 983030 for supplying of services for exposure visit within state. • While calling RFQ (Request for Quotation) and other documentations only shop license, GST registration certificate and PAN is requested. Since bid is called for food , travel and other ancillary services other licenses or registration should have been ask like FSSAI registration , National Permit, Bus fitment certificate should have been requested. But the same is not at all requested in tendering and same is not provided by any bidder. • One of the conditions of RFQ is that bus should be provided with push back seater arrangement, however, due to unavailability of sufficient record we are unable to vouch the same. • As explain to us detail guidelines relating to Exposure visit provided on 03/03/2023 and tour were conducted before 03/03/2023 | Low | 0
2 | 2023-03-31 | DIUAurangabad2 | 2 | Non-Monetary | Finance | Delay Settlement of Advances | Advance to ATM/ BTM provide for Farmer filed school in month of August 2022, September 2022 amounting Rs. 700000 and Rs. 260000 respectively which settled on 31.03.2023 which is not in accordance with guidelines in Project Finance Management Manual. | Low | 0
3 | 2023-03-31 | DIUAurangabad3 | 3 | Non-Monetary | Finance | Delay in submission of IUFR and PFS | IUFR Quarter I- Due Date of Submission=10/07/2022 Actual Date of Submission=Date not Available IUFR Quarter II- Due Date of Submission=10/10/2022 Actual Date of Submission=Date not Available IUFR Quarter III- Due Date of Submission=10/01/2023 Actual Date of Submission=Date not Available IUFR Quarter IV- Due Date of Submission=10/04/2023 Actual Date of Submission=Date not Available PFS 2022-23- Due Date of Submission=30/04/2023 Actual Date of Submission= Date not Available | Low | 0