## AuditPara
Audit Para Upload
Audit Ref. No. | SMART/2022-23/Ext/0600 PIUMCD
Bill No | Bill Date (yyyy-MM-dd) | PFMS No. | Para No. | Audit Category (Monetary/Non-Monetary) | Audit Section (Procurement/Technical/Finance/MIS/Others) | Audit Para Title | Audit Description | Severity (Critical/High/Medium/Low) | Para Amount (in Rs.)
1 | 2023-03-31 | PIUMCDC1 | 1 | Non-Monetary | Finance | IUFRs (Internal Unaudited Financial Reports) | It appears that the Project Implementation Unit (PIU) has not incurred any expenditure until September 2022, and consequently, IUFRs (Internal Unaudited Financial Reports) for Quarter 1 and Quarter 2 were not prepared | Low | 0
2 | 2023-03-31 | PIUMCDC2 | 2 | Non-Monetary | Technical | Observation Reletaed Advance to CBOs: 1) Shrirampur Pragat Bagayatdar Vivdh Karyakari Sahakari Sanstha : | It appears that there was a deviation from the Project Finance Manual in the splitting of the First Tranche into two parts (Rs. 6 Lakhs and Rs. 8.86 Lakhs) in the grant agreement. | Low | 0
3 | 2023-03-31 | PIUMCDC3 | 3 | Non-Monetary | Technical | Observation Reletaed Advance to CBOs: 2) Kharola Seva Society: | It appears that there was a deviation from the Project Finance Manual in the splitting of the First Tranche into Three parts (Rs. 4.24 Lakhs, Rs.10.85 Lakhs and Rs.25.95 Lakhs) in the grant agreement. | Low | 0
4 | 2023-03-31 | PIUMCDC4 | 4 | Non-Monetary | Technical | Observation Reletaed Advance to CBOs: 3) Nerpingalai Vivdh Karyakari Sahakari Sanstha : | It appears that there was a deviation from the Project Finance Manual in the splitting of the First Tranche into Three parts (Rs. 4.39 Lakhs, Rs.12.38 Lakhs and Rs.17.22 Lakhs) in the grant agreement. | Low | 0
5 | 2023-03-31 | PIUMCDC5 | 5 | Non-Monetary | Technical | Observation Reletaed Advance to CBOs: 4) Ahmedpur Vivdh Karyakari Sahakari Sanstha : | It appears that First Tranch was splite into Two Parts (Rs. 5.76 Lakhs and Rs.5.66 Lakhs) in grant agreement which is not in line with Project Finance Manual | Low | 0
6 | 2023-03-31 | PIUMCDC6 | 6 | Non-Monetary | Technical | Observation Reletaed Advance to CBOs: 5) Godavari Vivdh Karyakari Sahakari Sanstha : | It appears that First Tranch was splite into Three Parts (Rs. 1.99 Lakhs, Rs.16.07 Lakhs and Rs.14.60 Lakhs) in grant agreement which is not in line with Project Finance Manual | Low | 0
7 | 2023-03-31 | PIUMCDC7 | 7 | Non-Monetary | Technical | Observation Reletaed Advance to CBOs: 6) Wadala Vivdh Karyakari Sahakari Sanstha | It appears that First Tranch was splite into Two Parts (Rs. 6.36 Lakhs and Rs.31.66 Lakhs) in grant agreement which is not in line with Project Finance Manual | Low | 0
8 | 2023-03-31 | PIUMCDC8 | 8 | Non-Monetary | Technical | Observation Reletaed Advance to CBOs: 7) Yedneshwar Vivdh Karyakari Sahakari Sanstha : | It appears that First Tranch was splite into Three Parts (Rs. 5.66 Lakhs, Rs.14.00 Lakhs and Rs.17.02 Lakhs) in grant agreement which is not in line with Project Finance Manual | Low | 0