## AuditPara
Audit Para Upload
Audit Ref. No. | SMART/2025-26/Int/0120 DIUAU0120 DIUAU/Q1
Bill No | Bill Date (yyyy-MM-dd) | PFMS No. | Para No. | Audit Category (Monetary/Non-Monetary) | Audit Section (Procurement/Technical/Finance/MIS/Others) | Audit Para Title | Audit Description | Severity (Critical/High/Medium/Low) | Para Amount (in Rs.)
NA | 2025-05-28 | C052537517618 | 1 | Monetary | Procurement | Delay in document Verification | It was observed that payment of Rs. 82,215/- has been made to New Suvidha Travels for hiring of vehicle on a call basis, however, supporting documents such as the vehicle's RTO, Permit, insurance certificate, fitness certificate and PUC certificate etc are not provided to us for verification. Date of payment 28-05-2025 of Rs. 82,215 | High | 82215
NA | 2025-06-30 | NA | 2 | Monetary | Procurement | Incomplete Documents | We observed that under the contract between the Head PIU Agri and M/s Prakash Agro Plast (Malegaon), dated October 25, 2024, cotton picking bags were supplied to DIU Ch. Sambhaji Nagar. However, the following discrepancies were noted: Supply order dated 11.10.2024 1. Non-Submission of Required Documents as per GCC Clause 13.1 As per the Contract Agreement, Special Condition GCC Clause 13.1, the following documents were required to be submitted by the supplier before the arrival of the goods. However, these documents have not been submitted: • Three copies of the Supplier’s invoice addressed to the concerned District Implementation Unit, detailing item descriptions, quantities, unit prices, and total values. • Delivery note acknowledgement of receipt of goods of consignee. • Insurance certificate covering transit risks. • Manufacturer’s/Supplier’s warranty certificate. • Inspection certificate issued by the nominated inspection agency, along with the Supplier’s factory inspection report. | High | 0
NA | 2025-06-30 | NA | 3 | Monetary | Procurement | Incomplete Documents | The delivery memo is dated 11 October 2024, while, according to the DIU’s authorized representative, the picking bags were actually received on 28 October 2024. • Mode of transit and vehicle details are not mentioned. • The supplier did not submit the required e-way bill. • The 6,000 cotton picking bags were physically received on 28 October 2024. Subsequently, on 4 November 2024, DIU forwarded a sample to ICAR for testing. The test report, dated 8 November 2024, indicated that the actual GSM (grams per square meter) was 172.6, which is below the required range of 200 250 GSM. However, no documentation or records have been presented to us on the follow up actions or remediation procedure taken in response to this deviation. Rs.1638000 | High | 1638000
MBBC-126/ 24-25 | 2025-05-07 | NA | 4 | Monetary | Procurement | Incomplete Documents | 1. Non-Submission of Required Documents as per GCC Clause 13.1 According to the Contract Agreement (Special Conditions, GCC Clause 13.1), the supplier was required to submit the specified documents before the arrival of the goods. However, the storage bags were delivered on 10 February 2025, the required documents were submitted only after DIU’s letter dated 22 May 2025, and some of the following mandatory documents remain un submitted. • Insurance certificate (policy) covering transit risks. • Inspection certificate issued by nominated inspection agency. According to GCC Clause 13.1, if these documents are not received in time, the supplier is responsible for any consequent expenses. The failure to submit these documents has led to non-compliance with the contractual terms Date of Payment 07-05-2025 Rs.1638000 | High | 3498600