## AuditPara
Audit Para Upload
Audit Ref. No. | SMART/2025-26/Int/0124 DIUBE0124 DIUBE/Q1
Bill No | Bill Date (yyyy-MM-dd) | PFMS No. | Para No. | Audit Category (Monetary/Non-Monetary) | Audit Section (Procurement/Technical/Finance/MIS/Others) | Audit Para Title | Audit Description | Severity (Critical/High/Medium/Low) | Para Amount (in Rs.)
NA | 2025-04-04 | C042510772470 | 1 | Monetary | Finance | Incomplete Documentation | Payment has been made to Swarajya Shetkari Bachat Gat Pimpalner of Farmers Group Tal-Beed for purchase of Cotton Seeds but following some irregularities: 1) Declaration Certificate of Concern department verified by grader and Agri assistant not provided for audit verification. 2) Distribution register of farmer’s seed not provided for verification. Date of Payment: 04-04-2025 of Rs.51000 | Medium | 51000
NA | 2025-04-08 | C042510791480 | 2 | Monetary | Finance | Incomplete Documentation | Payment has been made to Shambhuraje Shetkari Bachat Gat Repewadi of Farmers Group Tal-Dharur for purchase of Cotton Seeds but following some irregularities: 1) Declaration Certificate of Concern department verified by grader and Agri assistant not provided for audit verification. 2) Distribution register of farmer’s seed not provided for verification. Date of Payment: 08-04-2025 of Rs.51000 | Medium | 51000
122 | 2025-03-15 | C052529335452 | 3 | Monetary | Finance | Incomplete Documentation | According to the contract’s GCC 16.1, payment of 100 % of the contract price is conditional upon: (a) submission of all documents required under SCC 13.1, and (b) issuance of an Acceptance Certificate by the consignee, upon successful supply, installation, and demonstration. However, as of 14 July 2025, no Acceptance Certificate has been issued by the consignee, indicating that SCC 13.1 requirements have not been fulfilled and successful delivery/installation has not taken place. In the absence of these mandatory conditions, no payment released but DIU Beed payment released to supplier. In light of the above, it is recommended that appropriate action be taken by the higher authority against the concerned parties to ensure accountability and adherence to contractual obligations. Date of Payment: 27-05-2025 of Rs.32,82,020 | High | 3282020
CPB/2 | 2025-07-01 | NA | 4 | Monetary | Finance | Incomplete Documentation | The delivery memo for cotton picking bags was not dated, which compromises the ability to verify the exact date of receipt. As per the available records, distribution was carried out on 30 December 2024. However, the distribution list was not properly prepared, resulting in a quantity mismatch. While a total of 6,000 cotton picking bags were received, the distribution list does not accurately account for the entire quantity distributed. This reflects weak inventory control and improper documentation. Date of Payment: 01-07-2025 of Rs.16,38,000/- | High | 1638000