## Sheet1
Audit Para Upload
Audit Ref. No. | SMART/2025-26/Int/0127 DIUCH0127 DIUCH/Q1
Bill No | Bill Date (yyyy-MM-dd) | PFMS No. | Para No. | Audit Category (Monetary/Non-Monetary) | Audit Section (Procurement/Technical/Finance/MIS/Others) | Audit Para Title | Audit Description | Severity (Critical/High/Medium/Low) | Para Amount (in Rs.)
RAPL/202425/11 | 2025-03-30 | C042511624107 | 1 | Monetary | Procurement | Delay in verification | a) Schedule of the exposure visit is not available for audit verification. b) Supporting feedback form is not available for audit verification. c) Geo Tagged photograph is not available for audit verification Date of Payment 05.04.2025 of Rs.Rs.308076/- | High | 308076
MBBC-125/24-25 | 2025-03-15 | C042534162316 | 2 | Monetary | Procurement | Delay in Supply | It was observed that under the contract between Head PIU Agri and M/s Maa Bhagwati Biotech & Chemical, dated October 25, 2024 (Supply Order No. 1562 dated 11.10.2024), for the supply of cotton storage bags to DIU Chandrapur, several discrepancies were noted. The supplier failed to submit required documents under GCC Clause 13.1—specifically, the transit insurance policy and inspection certificate with the factory inspection report—except for the delivery memo and invoices received on 15 March 2025. The delivery memo dated 05 January 2025 lacked verification of technical specifications, mode of transit, vehicle number, and e-way bill. A total of 3,400 bags were received on 06 January 2025, but only 3,375 were distributed as per records. Delivery was delayed by 42 days beyond the stipulated deadline of 24 November 2024, for which Rs. 1,39,944/- was deducted as liquidated damages. Further, the testing process showed procedural lapses—the sample was sent on 06 January 2025 to Superintendence Company of India Pvt. Ltd., Mumbai, and results were received on 27 January 2025; however, the lab’s ISO certification and textile testing authorization were not verified. The delay in testing and non-submission of mandatory documents indicate non-compliance with contractual provisions. It is recommended that higher authorities take appropriate action to ensure accountability and adherence to contract terms. Date of Payment 02.05.2025 Of Rs.3225376 | High | 3225376
CPB/ 4 | 2025-07-01 | C072554722563 | 3 | Monetary | Procurement | Non-Compliance in Supply | We observed that Under the contract with M/s Prakash Agro Plast (Malegaon) dated 25 October 2024 (Order No.1563), for supply of cotton picking bags to DIU Chandrapur, major non-compliances were noted. Required documents under GCC 13.1 were not submitted, and delivery was delayed beyond the stipulated period. The Acceptance Certificate was not issued, indicating incomplete compliance. Out of 6,000 bags received, testing by ICAR revealed GSM 163.20 against the required 200–250 range. Material was distributed before receipt of the test report, and replacement of defective goods was not done. Despite deviation, the supplier invoiced at a reduced rate without DIU’s approval, violating contract terms. Date of Payment 29.07.2025 of Rs.1299870/- | High | 1299870