## AuditPara
Audit Para Upload
Audit Ref. No. | SMART/2025-26/Int/0123 DIUAM0123 DIUAM/Q1
Bill No | Bill Date (yyyy-MM-dd) | PFMS No. | Para No. | Audit Category (Monetary/Non-Monetary) | Audit Section (Procurement/Technical/Finance/MIS/Others) | Audit Para Title | Audit Description | Severity (Critical/High/Medium/Low) | Para Amount (in Rs.)
NA | 2025-06-30 | NA | 1 | Non-Monetary | Procurement | Irregularities in Supply and Payment | Under the contract dated 25 October 2024 between Head PIU Agri and M/s Prakash Agro Plast (Malegaon) for the supply of 6,000 cotton picking bags to DIU Amravati, multiple discrepancies were observed. Mandatory documents as per GCC Clause 13.1—including invoices, delivery notes, insurance certificate, warranty, and inspection reports—were not submitted. The delivery deadline of 24 November 2024, as per GCC Clause 1.1(o), was not fully complied with, and no liquidated damages were imposed. Additionally, no Acceptance Certificate was issued under GCC Clause 16.1, yet payment was released despite non-compliance. Verification revealed that the delivery memo was undated, transit and vehicle details were missing, and the e-way bill was not submitted. ICAR testing showed the bags’ GSM (167.9) deviated from the required 200–250 GSM. DIU requested the supplier to collect or replace the non-conforming bags, but the supplier did not take remedial action, violating GCC Clauses 28.5 and 28.6. | High | 1638000
121 | 2025-03-15 | NA | 2 | Non-Monetary | Procurement | Irregularities in Supply and Payment | Under the contract dated 25 October 2024 between Head PIU Agri and Maa Bhagwati Biotech & Chemical for the supply of 3,400 cotton storage bags to DIU Amravati, several discrepancies were observed. Mandatory documents under GCC Clause 13.1—including insurance, warranty, and inspection certificates—were not submitted, and the delivery memo lacked transit and vehicle details. Sample testing was delayed by 74 days, and the testing laboratory’s ISO certification was not provided, contributing to a fire incident that destroyed the bags. The delivery deadline of 24 November 2024, as per GCC Clause 1.1(o), was not met, and no liquidated damages were imposed under GCC Clause 27.1. These issues indicate non-compliance with contractual obligations, and appropriate action is recommended to ensure accountability. | High | 3498600