## AuditPara
Audit Para Upload
Audit Ref. No. | SMART/2025-26/Int/0150 DIUWAR0150 DIUWAR/Q1
Bill No | Bill Date (yyyy-MM-dd) | PFMS No. | Para No. | Audit Category (Monetary/Non-Monetary) | Audit Section (Procurement/Technical/Finance/MIS/Others) | Audit Para Title | Audit Description | Severity (Critical/High/Medium/Low) | Para Amount (in Rs.)
NA | 2025-06-30 | NA | 1 | Monetary | Finance | Delay in Deposit | It has been observed that TDS deducted in June 2025 was deposited with the Government Authority up to 10 days late. Date of payment 07.07.2025 of Rs.12000/- | Medium | 12000
NA | 2025-06-30 | NA | 2 | Monetary | Finance | Delay in Payment | We observed that unit has made payment to Krushi vibhag karmachari Vrund sahkari pat santha Limited for office rent for month of April may & June but Rent Receipt copy not provided for verification. Date of payment 24.06.2025 of Rs.77532/- | High | 77532
MBBC-124/24-25 | 2025-03-15 | C0525232265289 | 3 | Monetary | Procurement | Delays in Supply | Under the contract between Head PIU Agri and M/s Maa Bhagwati Biotech & Chemical, dated 25 October 2024, for the supply of cotton storage bags to DIU Wardha (Supply Order dated 11 October 2024), several irregularities were noted. The supplier failed to submit mandatory documents as per GCC Clause 13.1, such as the warranty certificate, inspection report, and transit insurance policy. The delivery memo dated 2 December 2024 lacked essential details like the vehicle number, e-way bill, and technical verification. Although 3,400 bags were received, the testing process was delayed, and the ISO certification of the testing laboratory was not verified. The delivery was also delayed beyond the 30-day contract period, resulting in a deduction of ₹52,479 as liquidated damages. As of date, the required documents remain unsubmitted, indicating non-compliance with contract terms. | High | 3498600
NA | 2025-06-30 | NA | 4 | Monetary | Procurement | Non-Compliance of Supply | Under the contract between Head PIU Agri and M/s Prakash Agro Plast, Malegaon (dated 25 October 2024; Supply Order No.1562 dated 11 October 2024) for supply of cotton picking bags to DIU Wardha, several irregularities were noted. The supplier failed to submit mandatory documents as per GCC Clause 13.1, including invoices, transport details, insurance, warranty, and inspection certificates. Delivery of 6,000 bags on 29 October 2024 lacked e-way bill and vehicle details. ICAR test results dated 12 November 2024 showed a GSM of 160.3, below the required 200–250 range. Despite multiple communications from DIU and PIU (Agriculture), the supplier neither replaced nor collected the defective goods as of 14 July 2025. Further, no Acceptance Certificate was issued, indicating non-compliance with GCC Clauses 13.1, 16.1, 28.5, and 28.6, and payment remains withheld. | High | 0