## RIU_Amravati
Audit Para Upload
Audit Ref. No. | SMART/2023-24/Int/0100 PIUAG
Bill No | Bill Date (dd/mm/yyyy) | PFMS No. | Para No. | Audit Category (Monetary/Non-Monetary) | Audit Section (Procurement/Technical/Finance/MIS/Others) | Audit Para Title | Audit Description | Severity (Critical/High/Medium/Low) | Para Amount (in Rs.)
|  |  | 6 | Non-Monetary | Procurement | Discrepancies in compliance of record keeping in tranches to CBO | Payment has been made to NANDORI FARMER PRODUCER COMPANY LIMITED, CHANDRAPUR as 1st Tranche of Project Grant, however, following irregularities were noticed: a. Agreement executed on Photocopy of stamp paper was provided for verification | High
|  |  | 7 | Non-Monetary | Procurement | Discrepancies in compliance of record keeping in tranches to CBO | Payment has been made to RAGHUKUL AGRO PRODUCER COMPANY LIMITED, LATUR as 1st Tranche of Project Grant, however, following irregularities were noticed: a. Total Project Cost as per SPAC Committee: 243.78 Lakhs Total Project Cost as per Grant Agreement: 244.04 Lakhs – b. Time taken from stage of approval of CBO till the issue of 1st Tranche of Project Grant is significant, ultimately causing unnecessary delay to Project. Details of the same are as below • Date of Approval as selection of CBO – 21/04/2022 • Date of Payment of First Tranche Amount – 12/05/2023 • Total Time taken from Selection to Issue of First Tranche – Almost 12 Months. | High
|  |  | 8 | Non-Monetary | Procurement | Discrepancies in compliance of record keeping in tranches to CBO | Payment has been made to SUSTAIN AGRO PRODUCER COMPANY LIMITED, PUNE as 1st Tranche of Project Grant, however, following irregularities were noticed: a. Time taken from stage of approval of CBO till the issue of 1st Tranche of Project Grant is significant, ultimately causing unnecessary delay to Project. Details of the same are as below • Date of Approval as selection of CBO – 20/09/2022 • Date of Payment of First Tranche Amount – 12/05/2022 • Total Time taken from Selection to Issue of First Tranche – Almost 8 Months | High
|  |  | 9 | Non-Monetary | Procurement | Discrepancies in compliance of record keeping in tranches to CBO | Payment has been made to SAMARTH SONWATI FARMER PRODUCER COMPANY LIMITED as 1st Tranche of Project Grant, however, following irregularities were noticed: a. Time taken from stage of approval of CBO till the issue of 1st Tranche of Project Grant is significant, ultimately causing unnecessary delay to Project. Details of the same are as below • Date of Approval as selection of CBO – 12/09/2022 • Date of Payment of First Tranche Amount – 31/05/2022 • Total Time taken from Selection to Issue of First Tranche – Almost 8 Months | High
|  |  | 10 | Non-Monetary | Procurement | Discrepancies in compliance of record keeping in tranches to CBO | Payment has been made to SUPERAGRO HI-TECH PRODUCER COMPANY LIMITED, JALNA as 1st Tranche of Project Grant, however, following irregularities were noticed: a. Time taken from stage of approval of CBO till the issue of 1st Tranche of Project Grant is significant, ultimately causing unnecessary delay to Project. Details of the same are as below • Date of Approval as selection of CBO – 20/09/2022 • Date of Payment of First Tranche Amount – 31/05/2022 • Total Time taken from Selection to Issue of First Tranche – Almost 8 Month. | High
|  |  | 11 | Non-Monetary | Procurement | Discrepancies in compliance of record keeping in tranches to CBO | Payment has been made to SHETKARI MITRA FARMERS PRODUCER COMPANY LIMITED as 1st Tranche of Project Grant, however, following irregularities were noticed: a. Time taken from stage of approval of CBO till the issue of 1st Tranche of Project Grant is significant, ultimately causing unnecessary delay to Project. Details of the same are as below • Date of Approval as selection of CBO – 20/09/2022 • Date of Payment of First Tranche Amount – 20/06/2022 • Total Time taken from Selection to Issue of First Tranche – 10 Months b. Observations related to DPR of Shetkari Mitra Farmer Producer Company Limited • It is observed that for the purpose of financial projections the Loan schedule which was attested by company secretary was wrongly calculated. The repayment schedule is calculated further even after the principal amount was fully repaid. Thus, the repayment schedule shows the repayment of principal amount in negative. • The Section 6 “Assumptions” includes the assumptions made for revenue, cost & each expenditure for the financial projections. The amounts shown for revenue, cost and every expenditure are same. The question arises on acceptance of assumptions therefore leading to the validation of financial projections. • The balance sheet attached by the FPC is signed by the chartered accountant but it is not signed by the representatives of the said FPC. • The list of members attached by the CS of FPC shows paid up capital of Rs.3,00,000 which is not matched with the data of MCA. • It is observed that there is balance as Control Ticker (Liabilities-Assets) at the 7th year in financial projections. • To conclude from above points, it is observed that verification of financial projections was not done correctly. As the financial projections play pivot role in the DPR of FPC, the internal controls should exist in a stringent manner. | High
|  |  | 12 | Non-Monetary | Procurement | Discrepancies in compliance of record keeping in tranches to CBO | Payment has been made to CHANDANESHWAR AGRO PRODUCER COMPANY LIMITED as 1st Tranche of Project Grant, however, following irregularities were noticed: a. Time taken from stage of approval of CBO till the issue of 1st Tranche of Project Grant is significant, ultimately causing unnecessary delay to Project. Details of the same are as below • Date of Approval as selection of CBO – 20/09/2022 • Date of Payment of First Tranche Amount – 20/06/2023 • Total Time taken from Selection to Issue of First Tranche – 10 Months | High
|  |  | 13 | Non-Monetary | Procurement | Discrepancies in compliance of record keeping in tranches to CBO | Payment has been made to KAVATHEKRUSHIKRANTI FARMERS PRODUCER COMPANY LIMITED, SATARA as 1st Tranche of Project Grant, however, following irregularities were noticed: a. Time taken from stage of approval of CBO till the issue of 1st Tranche of Project Grant is significant, ultimately causing unnecessary delay to Project. Details of the same are as below • Date of Approval as selection of CBO – 20/09/2022 • Date of Payment of First Tranche Amount – 20/06/2023 • Total Time taken from Selection to Issue of First Tranche – 9 Months | High
|  |  | 14 | Non-Monetary | Procurement | Discrepancies in compliance of record keeping in tranches to CBO | Payment has been made to KISAN FIELDFRESH FARMER PRODUCER COMPANY LIMITED, SATARA as 1st Tranche of Project Grant, however, following irregularities were noticed: a. Time taken from stage of approval of CBO till the issue of 1st Tranche of Project Grant is significant, ultimately causing unnecessary delay to Project. Details of the same are as below • Date of Approval as selection of CBO – 08/03/2023 • Date of Payment of First Tranche Amount – 20/06/2023 • Total Time taken from Selection to Issue of First Tranche – 9 Months | High
|  |  | 15 | Non-Monetary | Procurement | Discrepancies in compliance of record keeping in tranches to CBO | Payment has been made to RAJBHAVAN FARMER PRODUCER COMPANY, JALANA as 1st Tranche of Project Grant, however, following irregularities were noticed: a. In Grant Agreement there are no signatures of witness. b. Time taken from stage of approval of CBO till the issue of 1st Tranche of Project Grant is significant, ultimately causing unnecessary delay to Project. Details of the same are as below • Date of Approval as selection of CBO – 20/09/2022 • Date of Payment of First Tranche Amount – 31/03/2023 • Total Time taken from Selection to Issue of First Tranche – 9 Months | High
|  |  | 16 | Non-Monetary | Procurement | Discrepancies in compliance of record keeping in tranches to CBO | a. Observations related to DPR of Shetkari Mitra Farmer Producer Company Limited • It is observed that Udyam registration in name of Krishna Farms/Krishna Kirtikumar Mangal is attached. • No MOA & AOA of the FPC was attached in DPR.-Not in checklist • In case of Projected cost of Plant & Machinery, GST Charges of Rs.43,74,342 is included which is not understood as no specific working was attached | High