## AuditPara
Audit Para Upload
Audit Ref. No. | SMART/2022-23/Ext/0129 DIUGO
Bill No | Bill Date (yyyy-MM-dd) | PFMS No. | Para No. | Audit Category (Monetary/Non-Monetary) | Audit Section (Procurement/Technical/Finance/MIS/Others) | Audit Para Title | Audit Description | Severity (Critical/High/Medium/Low) | Para Amount (in Rs.)
1 | 2023-03-31 | DIUGONDIA1 | 1 | Non-Monetary | Procurement | VCDS – Crop Demonstration | • As per VCDS procurement guidelines, GST number is to be mentioned on quotation and rates for the procurement should be inclusive of all taxes. However, in case of VCDS procurement dated 03-08-2022, Improper quotation were received from Bhaskar Agro Sales Corporation & Om Sai Krushi Kendra containing rates exclusive of taxes. However, their rates excluding gst are higher than the rate quote by Krushi Vikas Agency & Krushi Vikas Kendra. • Delivery of the procurement was not done within due time. Supply order dated 27/06/2022 clearly states the supply has to be provided within 14 days i.e., till 10/07/2022. But it was lately delivered on 26/07/2022. | Low | 0
2 | 2023-03-31 | DIUGONDIA2 | 2 | Non-Monetary | Finance | Delay Settlement of Advances | Advance to ATM/ BTM provide for Farmer filed school amounting to Rs. 1,60,000 were settled on 31.03.2023. AS per 11.4 of second amended FMM, it has to be settled within 1 month of completion of event. i.e., within one month of last farmer field school. | Low | 0
3 | 2023-03-31 | DIUGONDIA3 | 3 | Non-Monetary | Finance | Delay in submission of IUFR and PFS | IUFR Quarter I- Due Date of Submission=10/07/2022 Actual Date of Submission=Not submitted IUFR Quarter II- Due Date of Submission=10/10/2022 Actual Date of Submission=10/10/2022 IUFR Quarter III- Due Date of Submission=10/01/2023 Actual Date of Submission=14/02/2023 IUFR Quarter IV- Due Date of Submission=10/04/2023 Actual Date of Submission=26/04/2023 PFS 2022-23- Due Date of Submission=30/04/2023 Actual Date of Submission=26/04/2023 | Low | 0
4 | 2023-03-31 | DIUGONDIA4 | 4 | Non-Monetary | Finance | TDS Challan were late paid | 1) Month of Payment- May,2022 TDS Paid & deducted-1011/- Due Date of Payment-07/06/2022 Date of Payment-12/08/2022 2) Month of Payment- June,2022 TDS Paid & deducted-1160/- Due Date of Payment-07/07/2022 Date of Payment-27/07/2022 3) Month of Payment- July,2022 TDS Paid & deducted-1160/- Due Date of Payment-07/08/2022 Date of Payment-08/08/2022 4) Month of Payment- Sept,2022 TDS Paid & deducted-1150/- Due Date of Payment-07/10/2022 Date of Payment-14/11/2022 5) Month of Payment- Oct,2022 TDS Paid & deducted-22300/- Due Date of Payment-07/11/2022 Date of Payment-14/11/2022 | Low | 0