## AuditPara
Audit Para Upload
Audit Ref. No. | SMART/2022-23/Ext/0131 DIUJAG
Bill No | Bill Date (yyyy-MM-dd) | PFMS No. | Para No. | Audit Category (Monetary/Non-Monetary) | Audit Section (Procurement/Technical/Finance/MIS/Others) | Audit Para Title | Audit Description | Severity (Critical/High/Medium/Low) | Para Amount (in Rs.)
1 | 2023-03-31 | DIUJALGAON1 | 1 | Non-Monetary | Finance | Delay Settlement of Advances | Advance to ATM/ BTM provide for Farmer filed school in month of July, August, September, 2022 was settled in March, 2023 and not in accordance with Project Finance Management Manual. It should be settled within one month from the conclusion of last farmer field school. | Low | 0
2 | 2023-03-31 | DIUJALGAON2 | 2 | Non-Monetary | Finance | SMART Cotton – Crop Demonstration | GST TDS was not deducted on the payment of Rs. 20,25,000/- | Low | 0
3 | 2023-03-31 | DIUJALGAON3 | 3 | Non-Monetary | Finance | VCDS – Crop Demonstration | GST TDS was not deducted on the payment of Rs. 4,17,198/- | Low | 0
4 | 2023-03-31 | DIUJALGAON4 | 4 | Non-Monetary | Finance | Delay in submission of IUFR and PFS | IUFR Quarter I- Due Date of Submission=10/07/2022 Actual Date of Submission=22/07/2023 IUFR Quarter II- Due Date of Submission=10/10/2022 Actual Date of Submission=17/10/2023 IUFR Quarter III- Due Date of Submission=10/01/2023 Actual Date of Submission=11/01/2023 IUFR Quarter IV- Due Date of Submission=10/04/2023 Actual Date of Submission=31/03/2023 PFS 2022-23- Due Date of Submission=30/04/2023 Actual Date of Submission=31/03/2023 | Low | 0