## AuditPara
Audit Para Upload
Audit Ref. No. | SMART/2025-26/Int/0132 DIUJA0132 DIUJA/Q1
Bill No | Bill Date (yyyy-MM-dd) | PFMS No. | Para No. | Audit Category (Monetary/Non-Monetary) | Audit Section (Procurement/Technical/Finance/MIS/Others) | Audit Para Title | Audit Description | Severity (Critical/High/Medium/Low) | Para Amount (in Rs.)
2450 | 2025-05-20 | NA | 1 | Monetary | Procurement | Irregularities in payment | Payment has been made to Anand Travel for exposure visit at Indore for 80 participant but following irregualrities were noticed a) Experience of having successfully completed similar types of work for any government organization , only government experience from Maharashtra to out of state having 7 days experience is not fulfilled by 3rd bidder Vedika tourism b) Training report, feedback form and other supporting not available for audit verification Date of payment 04.06.2025 of Rs.1585080/- | High | 1585080
MBBC-123/24-25 | 2025-05-20 | C052526856674 | 2 | Monetary | Procurement | Irregularities in Supply and Payment | Under the contract between Head PIU Agri and Maa Bhagwati Biotech & Chemical dated 25 October 2024 for the supply of cotton storage bags to DIU Jalna, several irregularities were observed. As per GCC Clause 13.1, mandatory documents such as the insurance policy, inspection certificate, factory inspection report, and warranty certificate were not submitted, except for the delivery memo, three invoices, and a test report. The e-way bill corresponding to the delivery memo dated 27 March 2025 was also not furnished. Further, the laboratory report dated 19 December 2024 from ICAR CIRCOT revealed multiple deviations from the technical specifications, including missing capacity and humidity details, only five nylon belts instead of six, three hooks instead of four, absence of the required sticker, and reduced height (67 cm instead of 69 cm). As per GCC Clause 1.1(o), the delivery was to be completed within 30 days from the contract date (i.e., by 24 November 2024). Although DIU deducted liquidated damages of ₹ 52,479 as per GCC Clause 27.1, the supplier still failed to submit the required documents. Moreover, as per GCC Clause 16.1, payment should only be released after submission of all documents and issuance of an Acceptance Certificate. However, no Acceptance Certificate was issued, and DIU Jalna released payment of ₹ 33,12,841 on 20 May 2025, indicating non-compliance with contractual terms. | High | 3312841
CPB/1 | 2025-07-21 | C072545667239 | 3 | Monetary | Procurement | Irregularities in Supply and Payment | Under the contract between Head PIU Agri and M/s Prakash Agro Plast (Malegaon) dated 25 October 2024 for the supply of cotton picking bags to DIU Jalna, several irregularities were observed. As per GCC Clause 13.1, mandatory documents such as the insurance certificate, inspection and factory reports, and warranty certificate were not submitted, leading to non-compliance with contractual terms. Although the supplier failed to provide these documents within the delivery period ending 24 November 2024, DIU Jalna did not deduct any liquidated damages as required under GCC Clause 27.1. Further, no Acceptance Certificate was issued as per GCC Clause 16.1, yet full payment was released to the supplier. Verification revealed that 6,000 cotton picking bags were received between 27–29 October 2024, with no sample testing, stock register, or distribution details made available for audit. Additionally, while the contract rate was ₹ 273 per bag (inclusive of GST), the supplier’s invoice reflected a lower rate of ₹ 225.23 per bag. | High | 1299870