## AuditPara
Audit Para Upload
Audit Ref. No. | SMART/2024-25/Ext/2000 PIUVST
Bill No | Bill Date (yyyy-MM-dd) | PFMS No. | Para No. | Audit Category (Monetary/Non-Monetary) | Audit Section (Procurement/Technical/Finance/MIS/Others) | Audit Para Title | Audit Description | Severity (Critical/High/Medium/Low) | Para Amount (in Rs.)
NA | 2025-03-31 | NA | 1 | Monetary | Procurement | Non-Completion of Contractual Deliverables by TSP | We observed that payment has been made to Grant thornton India Ltd LLP for consulting services as TSP for CSC however following irregularities noticed. a. Only 5 CSC’s are established and 1 is pending. b. Creation & Operationalization of Digital platform for Most of the CSCs are pending as follows. • Digital platform has been done by CSC in case of IGDC/IFDC however operationalization is pending. • Operationalization of Digital platform is pending in case of ISDA. • Creation in process & operationalization is pending in case of IMMDA. • Creation in process & operationalization is pending in case of IMMDA. c. Governance & Administrative Support-Only 1 BOD Meeting conducted in case of ICDA CSC. d. Participation in International events, Trade Fairs, Sectoral seminars/Workshop etc pending. e. Conducting meeting of Policy Dialogue Groups is pending for 3 CSCs. f. Approval of VSTF for delay in deliverables required as the same is hampering the progress of the project. | High | 12592604
NA | 2025-03-31 | NA | 2 | Monetary | Others | Delay in documentation | We Observed that PIU-VSTF has made payment to Following CBO’s but PFMS Copy and Updated Bank statement not provided for audit verification. Date of payment 28/05/24 of Rs.7433000 | Medium | 7433000