## AuditPara
Audit Para Upload
Audit Ref. No. | SMART/2024-25/Ext/0154 VAN
Bill No | Bill Date (yyyy-MM-dd) | PFMS No. | Para No. | Audit Category (Monetary/Non-Monetary) | Audit Section (Procurement/Technical/Finance/MIS/Others) | Audit Para Title | Audit Description | Severity (Critical/High/Medium/Low) | Para Amount (in Rs.)
Smart-14 | 2024-01-29 | C042401648795 | 1 | Monetary | Procurement | Discrepancies in Billing and Supporting Documents for CBO Training | We observed that unit payment has been made to Regional Agriculture Extension Management Training Institute (RAMETI) At-Amravati for CBO's Training at Rameti level but following some irregularities: (Training Period 10/01/2024 to 12/01/2024) a) As per the guidelines, a minimum of 22 trainees were required for the training; however, only 20 trainees attended, as per the attendance sheet. Despite this, a bill was submitted for 40 trainees, and payment was disbursed accordingly. Furthermore, the guidelines clearly state that if fewer than 22 participants are present, the training must be cancelled and rescheduled only when the required minimum of 22 trainees is available. Therefore, the payment amount paid should be treated as irregular and must be recovered from the concerned person. b) Photographic evidence shows only 11 members present during the training. A list of 30 trainees was prepared; however, the attendance sheet confirms the presence of only 20 trainees. c) Training Completion Certificate not provided for audit verification d) Extra cost should be recovered from participants who first agreed to be present but later denied Date of payment 06/04/2025 of Rs. 180000 | High | 180000
NA | 2025-03-31 | C052412091118 | 2 | Monetary | Procurement | Discrepancies in Billing and Supporting Documents for CBO Training | We observed that unite payment has been made to Regional Agriculture Extension Management Training Institute (RAMETI) At-Nagpur for CBO's Training at Rameti level but Training Completion Certificate not provided for audit verification. (Training Period 26/03/2024 to 28/03/2024) a) The tax invoice submitted does not mention the Bill Number and Bill Date. b) As per records, the actual total participation was 24 trainees for 3 days, and at the approved rate of ₹1,500 per trainee per day, the total payable amount should be ₹1,08,000 (24 x 3 x ₹1,500). However, a bill of ₹1,80,000 was submitted. c) Training Completion Certificate not provided for audit verification. Date of payment 14/05/2025 of Rs.180000 | High | 180000