## Sheet1
Audit Para Upload
Audit Ref. No. | SMART/2025-26/Int/0132 DIUJA0132 DIUJA/Q1
Bill No | Bill Date (yyyy-MM-dd) | PFMS No. | Para No. | Audit Category (Monetary/Non-Monetary) | Audit Section (Procurement/Technical/Finance/MIS/Others) | Audit Para Title | Audit Description | Severity (Critical/High/Medium/Low) | Para Amount (in Rs.)
MBBC-123/24-25 | 2025-04-01 | C052526856674 | 1 | Monetary | Procurement | Irregularities in Supply and Payment | Under the contract between Head PIU Agri and Maa Bhagwati Biotech & Chemical dated 25 October 2024 for the supply of cotton storage bags to DIU Jalna, several irregularities were observed. As per GCC Clause 13.1, mandatory documents such as the insurance policy, inspection certificate, factory inspection report, and warranty certificate were not submitted, except for the delivery memo, three invoices, and a test report. The e-way bill corresponding to the delivery memo dated 27 March 2025 was also not furnished. Further, the laboratory report dated 19 December 2024 from ICAR CIRCOT revealed multiple deviations from the technical specifications, including missing capacity and humidity details, only five nylon belts instead of six, three hooks instead of four, absence of the required sticker, and reduced height (67 cm instead of 69 cm). As per GCC Clause 1.1(o), the delivery was to be completed within 30 days from the contract date (i.e., by 24 November 2024). Although DIU deducted liquidated damages of ₹ 52,479 as per GCC Clause 27.1, the supplier still failed to submit the required documents. Moreover, as per GCC Clause 16.1, payment should only be released after submission of all documents and issuance of an Acceptance Certificate. However, no Acceptance Certificate was issued, and DIU Jalna released payment of ₹ 33,12,841 on 20 May 2025, indicating non-compliance with contractual terms. | High | 3312841