## AuditPara
Audit Para Upload
Audit Ref. No. | SMART/2022-23/Ext/0150 DIUWAR
Bill No | Bill Date (dd/mm/yyyy) | PFMS No. | Para No. | Audit Category (Monetary/Non-Monetary) | Audit Section (Procurement/Technical/Finance/MIS/Others) | Audit Para Title | Audit Description | Severity (Critical/High/Medium/Low) | Para Amount (in Rs.)
1 | 2023-03-31 | DIUWARDHA1 | 1 | Monetary | Procurement | VCDS CROP DEMONSTRATION/ SMART COTTON DEMONSTRATION | VCDS CROP DEMONSTRATION 25/06/2022 Direct payment has been made to 30 farmers of Rs. 2,039 each totalling to Rs. 61170 for the purchase of fertilizers on their own. As per VCDS circulars, DIU is required to procure the material to be distributed to farmers under VCDS Crop Demonstration. Direct Distribution of funds not allowed except Rs. 1000 under critical practices. 06/03/2023 Direct payment has been made to 30 farmers of Rs. 2350 each out of which Rs. 1350 totalling to Rs. 40500 for the purchase of fertilizers on their own. As per VCDS circulars, DIU is required to procure the material to be distributed to farmers under VCDS Crop Demonstration. Direct Distribution of funds not allowed except Rs. 1000 under critical practices. 11/03/2023 Direct payment has been made to 30 farmers of Rs. 1532 each out of which Rs. 532 totalling to Rs. 15,960 for the purchase of fertilizers on their own. As per VCDS circulars, DIU is required to procure the material to be distributed to farmers under VCDS Crop Demonstration. Direct Distribution of funds not allowed except Rs. 1000 under critical practices. 15/03/2023 Direct payment has been made to 25 farmers of Rs. 2350 each out of which Rs. 1350 totalling to Rs. 33,750 for the purchase of fertilizers on their own. As per VCDS circulars, DIU is required to procure the material to be distributed to farmers under VCDS Crop Demonstration. Direct Distribution of funds not allowed except Rs. 1000 under critical practices. TRAINING CUM EXPOSURE VISIT 12 farmers were selected for out of state training of agriculture activity conducted in Ludhiana, Punjab. However only utilization certificate has been provided to us for verification. Details, Bills were not available on record for verification. Utilization Certificate were provided by ICAR- CIPHET of Rs. 1,43,440 Part II: Inadmissible Expenses wherein expenses are excessive, no proper supporting available, or expenses were not as per procurement guidelines hence considered as inadmissible. SMART COTTON DEMONSTRATION 01/08/2022 Procurement of seeds to be distributed to farmers in Devali Taluka was done from Omkar Agro Engineering Company for the amount of Rs.20,52,000, following discrepancies were observed during audit period – • As per revised guidelines of VCDS SMART COTTON PROCUREMENT, any procurement above Rs. 10 lakh is to be done through online quotation on MAHATENDER site or GEMS portal. But in this case, procurement was done through offline mode after advertisement in newspaper. • Income Tax Return, Shop Act license were not available on record. • TDS challan were late paid. 17/09/2022 Procurement of Cotton Collection Kit to be distributed to farmers was done from Snehal Readymade Clothes and Generals for the amount of Rs.8,28,900, following discrepancies were observed during audit period – • As per procurement manual, Procurement has to be done from GST registered vendor. However, Vendor was not registered under GST at the time of procurement. • Quotation was not called from GST registered vendors. • GST certificates of other vendors were not available for verification. | High | 1123720
2 | 2023-03-31 | DIUWARDHA2 | 2 | Non-Monetary | Procurement | VCDS CROP DEMONSTRATION | · Nimboli Ark purchased for distribution to farmers was procured as per VCDS guidelines but RFQ is incomplete and also comparison chart was not complete. • Fixed Asset (Projector) purchased during the audit period were not numbered serially. • TAN & GST number were obtained in August, 2022. • Farmer Field School which was conducted in last year was presented for payment in current audit period i.e., FY 2022-23. Bills has to be settled within 1 month of completion of FFS. • Advances which were provided to various members for conducting FFS was lately settled in march 2023. Such advances have to be settled within 1 month of completion of FFS. • Only Salary TDS & PT challan of MAHACOT graders salary were paid directly to treasury from DIU office. Rest all the deductions was transferred to MAHACOTT account. • PFS has been submitted to HO on 10/04/2023 but not yet approved. | low | 0
3 | 2023-03-31 | DIUWARDHA3 | 3 | Non-Monetary | Finance | IUFR & PFS | IUFR Quarter I- Due Date of Submission=10/07/2022 Actual Date of Submission=Not Submited IUFR Quarter II- Due Date of Submission=10/10/2022 Actual Date of Submission= 04/10/2022 IUFR Quarter III- Due Date of Submission=10/01/2023 Actual Date of Submission=25/01/2023 IUFR Quarter IV- Due Date of Submission=10/04/2023 Actual Date of Submission=10/04/2023 PFS 2022-23- Due Date of Submission=30/04/2023 Actual Date of Submission= 10/04/2023 | low | 0