## AuditPara
Audit Para Upload
Audit Ref. No. | SMART/2024-25/Ext/0120 DIUAU
Bill No | Bill Date (yyyy-MM-dd) | PFMS No. | Para No. | Audit Category (Monetary/Non-Monetary) | Audit Section (Procurement/Technical/Finance/MIS/Others) | Audit Para Title | Audit Description | Severity (Critical/High/Medium/Low) | Para Amount (in Rs.)
NA | 2025-03-31 | NA | 1 | Non-Monetary | Procurement | IRREGULITIES IN DOCUMENTATION | It was observed that under the contract dated 25.10.2024 with M/s Prakash Agro Plast, the supplier failed to comply with key contractual conditions. Mandatory documents as prescribed under SCC/GCC Clause 13.1 were not submitted to the consignee. The delivery timeline as per GCC Clause 1.1(o) and related provisions on liquidated damages under GCC Clause 27.1 were not properly complied with, as delivery documentation was incomplete and inconsistent. Further, no Acceptance Certificate was issued as required under GCC Clause 16.1, though payment-related details were not produced for audit verification. Additionally, discrepancies were noted in delivery dates, absence of e-way bill and transit details, and quality shortfall, as ICAR test results showed GSM below the specified range, with no evidence of corrective or follow-up action. | HIgh | 1638000
MBBC-126/ 24-25 | 2025-03-15 | NA | 2 | Non-Monetary | Procurement | Non-Compliance in Documentation, Delivery Timeline, and Quality of Cotton Storage Bags | We observed that under the contract between the Head PIU Agri and Maa Bhagwati biotech & chemical, dated October 25, 2024, cotton storage bags were supplied to DIU CH. Sambhaji Nagar. However, the following discrepancies were noted: Supply order dated 11.10.2024 1. Non-Submission of Required Documents as per GCC Clause 13.1 According to the Contract Agreement (Special Conditions, GCC Clause 13.1), the supplier was required to submit the specified documents before the arrival of the goods. However, the storage bags were delivered on 10 February 2025, the required documents were submitted only after DIU’s letter dated 22 May 2025, and some of the following mandatory documents remain un submitted. • Insurance certificate (policy) covering transit risks. • Inspection certificate issued by nominated inspection agency. According to GCC Clause 13.1, if these documents are not received in time, the supplier is responsible for any consequent expenses. The failure to submit these documents has led to non-compliance with the contractual terms 2. As per the delivery memo, the DIU representative signed to confirm that the storage bags were actually delivered at DIU on 10 February 2025. However, the e way bill indicates that the goods were dispatched between 6 January 2025 and 8 January 2025. 3. According to the delivery memo dated 31 December 2024 and the receiver’s signature dated 10 February 2025, a total of 3,400 cotton storage bags were received at DIU. A sample of these bags was submitted to Shivmalhar Laboratories, Hingna on 27 February 2025. The laboratory test report, received belatedly on 03 March 2025, indicates that the bags do not conform to the contract’s required technical specifications because: i) The report fails to state the cotton humidity in the Date of payment 07.05.2025 of Rs.3498600 | HIgh | 3498600
NA | 2025-03-31 | NA | 3 | Non-Monetary | Others | Short Payment and Non-Submission of Professional Tax Returns | It was observed that Professional Tax liability for FY 2024-25 was 13500/- but only 13300/- was paid and remaining 200/- for the month of May-2024 was pending till march 2025. Also PT return filing acknowledgements were not provided for audit verification. ( Kindly refer annexure 1 ) | HIgh | 0