## AuditPara
Audit Para Upload
Audit Ref. No. | SMART/2024-25/Ext/0132 DIUJA
Bill No | Bill Date (yyyy-MM-dd) | PFMS No. | Para No. | Audit Category (Monetary/Non-Monetary) | Audit Section (Procurement/Technical/Finance/MIS/Others) | Audit Para Title | Audit Description | Severity (Critical/High/Medium/Low) | Para Amount (in Rs.)
CPB/1 | 2025-07-01 | C072545667239 | 1 | Monetary | Others | Irregularities in Payment and Documentation | We observed non-compliances in the supply of 6,000 cotton picking bags to DIU Jalna under the contract dated 25.10.2024 with M/s Prakash Agro Plast. Mandatory documents under GCC Clause 13.1, including transit insurance, inspection certificate, and warranty certificate, were not submitted, resulting in contractual non-compliance. Delivery was delayed beyond the stipulated deadline of 24.11.2024, yet no liquidated damages were recovered as per GCC Clause 27.1. No Acceptance Certificate was issued by the consignee as required under GCC Clause 16.1, but payment was released despite incomplete documentation. Discrepancies were noted between the delivery memo (11.10.2024) and actual receipt dates (27–29.10.2024), and no evidence of sample testing, distribution records, or stock registers was provided. Additionally, the supplier invoiced Rs. 225.23 per bag, lower than the contractually agreed rate of Rs. 273 per bag, indicating further irregularity in payment and compliance. date of payment 21.07.2025 of Rs. 1299870 | High | 1299870
MBBC-123/24-25 | 2025-03-15 | C052526856674 | 2 | Monetary | Others | Irregularities in Payment and Documentation | We observed the supply of 3,400 cotton storage bags to DIU Jalna under the contract dated 25.10.2024 with M/s Maa Bhagwati Biotech & Chemical revealed multiple non-compliances. Mandatory documents under GCC Clause 13.1, including transit insurance, inspection certificate, factory inspection report, and warranty certificate, were not submitted, and the e-way bill was also missing. Delivery was delayed beyond the stipulated deadline of 24.11.2024, though liquidated damages of Rs. 52,479 were deducted. ICAR CIRCOT testing of samples indicated several technical deviations, including incorrect capacity, missing belts and hooks, absent stickers, and reduced bag height. No Acceptance Certificate was issued as required under GCC Clause 16.1, yet payment was released despite incomplete documentation and non-compliance with contractual obligations, highlighting significant procedural, delivery, and quality lapses. Date of payment 20.05.2025 of Rs.3312841 | High | 3312841
NA | 2025-03-31 | NA | 3 | Monetary | Procurement | Irregularities Printing Procurement | We observed that payment has been made to yash multiservice jalna for printing cotton booklet & Mahiti pustika but quotation process is not followed properly. Bidder details Sr. No. Name of the Party Status 1. yash multiservice jalna Qualified 2. shikant paper product Qualified 3. vilas offset printers Disqualified Qty 600 unit rate.141 total amt. 84600 Size. 1/8 size 4 colour ,170,gsm 1. .All three- party quotation Open by me signature of Minimum 5 procurement committee member is not found on record 2. Geo tag photograph not provided for verification Date of payment 01.01.2025 of Rs. 84600 | High | 84600
NA | 2025-03-31 | C122422134725 / C122422134725 | 4 | Monetary | Procurement | Delay in documentation | It was noticed that payment has been made to the Shetkari Bachat Gat amounting to Rs. 1036800 /- for Market Led Cotton Demonstration, for the distribution of cotton demos to its SHG members, however, following documents were not found on record and not presented to us for audit verification such as: • Resolution Copy passed by the SHG • SHG Registration copy with ATMA not provided for audit verification • Demand copy of SHG as submitted to ATMA not provided for audit verification • NOC Of the member farmer were not provided for audit verification • SHG Passbook not provided for audit verification • Tax invoice of farmer as submitted to SHG not provided Date of payment 10.12.2024 of Rs. 1036800 | High | 1036800
NA | 2025-03-31 | C122413161796 | 5 | Monetary | Procurement | Missing Documentation | It was noticed that payment has been made to the Shetkari Bachat Gat amounting to Rs. 984960 /- for Market Led Cotton Demonstration, for the distribution of cotton demos to its SHG members, however, following documents were not found on record and not presented to us for audit verification such as: • Resolution Copy passed by the SHG • SHG Registration copy with ATMA not provided • Demand copy of SHG as submitted to ATMA not provided • NOC Of the member farmer were not provided • SHG Passbook not provided for audit verification • Tax invoice of farmer as submitted to SHG not provided • Certification copy of agriculture officer not provided • UC Not provided for audit verification | High | 984960
NA | 2025-03-31 | C122413037714 | 6 | Monetary | Procurement | Missing Documentation | It was noticed that payment has been made to the ATM /BTM Rs. 1500000 /- for farmer field school , for training of smart cotton however, following documents were not found on record and not presented to us for audit verification such as • Shetishala ahwal Not provided • Geo tag photograph copy not provided • Training Attendance register not provided • Food Bill copy ,labour charges ,UC Not provided • Details of farmer not provided • Attendance register not provided • Information of cotton Booklet details not provided | High | 1500000
NA | 2025-03-31 | NA | 7 | Non-Monetary | Others | Delay in documentation | During the audit verification, it was observed that, PT acknowledgment copies have not been provided to us. ( kindly refer annexure 1 ) | High | 0
NA | 2025-03-31 | NA | 8 | Non-Monetary | Others | Delay in documentation | During the audit verification, it was observed that, 192 acknowledgment copies have not been provided to us. ( kindly refer annexure 1 ) | High | 0
NA | 2025-03-31 | NA | 9 | Non-Monetary | Others | Delay in documentation | During the audit verification, it was observed that, 194 C acknowledgment copies have not been provided to us. ( kindly refer annexure 1 ) | High | 0
NA | 2025-03-31 | NA | 10 | Non-Monetary | Others | Delay in documentation | During the audit verification, it was observed that the GSTR-7 return filing acknowledgment copies have not been provided to us. ( kindly refer annexure 1 ) | High | 0