## AuditPara
Audit Para Upload
Audit Ref. No. | SMART/2020-21/Int/0000 PCMU
Bill No | Bill Date (dd/mm/yyyy) | PFMS No. | Para No. | Audit Category (Monetary/Non-Monetary) | Audit Section (Procurement/Technical/Finance/MIS/Others) | Audit Para Title | Audit Description | Severity (Critical/High/Medium/Low) | Para Amount (in Rs.)
46/20-21 | 2020-04-01 | C072012173094 | 1 | Monetary | Procurement | Expression of Interest | M/s. Shri Shivkripa Services (House Keeping) We had observed that payment has been made to M/s Shri Shivkripa services for Housekeeping services but following irregularities were noticed: a. As per work order, vendor shall require entering into the agreement within 15 days from the date of work order, however, date of work order was 30.11.2019 and date of agreement was 23.01.2020.- b. As per quotation terms No. 5 (4), vendor shall require to give a security deposit of Rs. 50,000/- in the form of DD/ cheque within 10 days from date of award of contract, however, proof of depositing DD/ Cheque were not made available to us for our verification. | Medium | 20,567
146/20-21 | 2020-05-02 | C072012173094 | 2 | Monetary | Procurement | Expression of Interest | M/s. Shri Shivkripa Services (House Keeping) We had observed that payment has been made to M/s Shri Shivkripa services for Housekeeping services but following irregularities were noticed: a. As per work order, vendor shall require entering into the agreement within 15 days from the date of work order, however, date of work order was 30.11.2019 and date of agreement was 23.01.2020.- b. As per quotation terms No. 5 (4), vendor shall require to give a security deposit of Rs. 50,000/- in the form of DD/ cheque within 10 days from date of award of contract, however, proof of depositing DD/ Cheque were not made available to us for our verification. | Medium | 20,567
260/20-21 | 2020-06-01 | C072012173094 | 3 | Monetary | Procurement | Expression of Interest | M/s. Shri Shivkripa Services (House Keeping) We had observed that payment has been made to M/s Shri Shivkripa services for Housekeeping services but following irregularities were noticed: a. As per work order, vendor shall require entering into the agreement within 15 days from the date of work order, however, date of work order was 30.11.2019 and date of agreement was 23.01.2020.- b. As per quotation terms No. 5 (4), vendor shall require to give a security deposit of Rs. 50,000/- in the form of DD/ cheque within 10 days from date of award of contract, however, proof of depositing DD/ Cheque were not made available to us for our verification. | Medium | 20,567
1369/20-21 | 2021-01-02 | C012114477778 | 4 | Monetary | Procurement | Expression of Interest | M/s. Shri Shivkripa Services (House Keeping) We had observed that payment has been made to M/s Shri Shivkripa services for Housekeeping services but following irregularities were noticed: a. As per work order, vendor shall require entering into the agreement within 15 days from the date of work order, however, date of work order was 30.11.2019 and date of agreement was 23.01.2020.- b. As per quotation terms No. 5 (4), vendor shall require to give a security deposit of Rs. 50,000/- in the form of DD/ cheque within 10 days from date of award of contract, however, proof of depositing DD/ Cheque were not made available to us for our verification. | Medium | 20,567
1183/20-21 | 2020-12-03 | C122012556877 | 5 | Monetary | Procurement | Expression of Interest | M/s. Shri Shivkripa Services (House Keeping) We had observed that payment has been made to M/s Shri Shivkripa services for Housekeeping services but following irregularities were noticed: a. As per work order, vendor shall require entering into the agreement within 15 days from the date of work order, however, date of work order was 30.11.2019 and date of agreement was 23.01.2020.- b. As per quotation terms No. 5 (4), vendor shall require to give a security deposit of Rs. 50,000/- in the form of DD/ cheque within 10 days from date of award of contract, however, proof of depositing DD/ Cheque were not made available to us for our verification. | Medium | 20,567
B380 | 2020-11-09 | C012135524040 | 6 | Monetary | Procurement | Expression of Interest | Durian Industries Ltd Supply of Executive chairs, sofa set & the installation of the same should have been done within 60 days from order copy, however, order copy is dated 27.03.2020 and bill dated 09.11.2020. This is not complied. | Medium | 615129
B402 | 2020-11-25 | C012135522775 | 7 | Monetary | Procurement | Expression of Interest | Durian Industries Ltd Supply of Executive chairs, sofa set & installation of the same should have been done within 60 days from order copy, however, order copy is dated 27.03.2020 and bill date is 25.11.2020. | Medium | 1452286
| 2020-12-02 | C122012545697 | 8 | Monetary | Procurement | Expression of Interest | Hathway Cable & Datacom Ltd. We observed that unit has made payment to Hathway cable & Datacom Ltd. for internet connectivity however, following irregularities were noticed: a. Quotation is received from three parties such as 1) You Broadband India Ltd. 2) Hathway Cable & Datacom Ltd. 3) Tikona infinite Pvt. Ltd. b. Date from which the service should be provided by Hathway cable & Datacom is not mentioned in the work order.- c. Quotation terms & conditions including scope were not mentioned on internet connection agreement.- | Medium | 43267
B4 | 2020-10-18 | C112023588405 | 9 | Monetary | Procurement | Expression of Interest | Sona Enterprises We observed that unit has made payment to Sona Enterprises for repairing of toilet and following irregularities were noticed: Work Order:27.03.2020 a. Agreement is not on stamp paper. | Medium | 562518
MOC/20-21/0227 | 2020-09-04 | C112023546915 | 10 | Monetary | Procurement | Expression of Interest | M/s. Oswal Ceramics We observed that unit has made payment to Oswal Ceramics for purchasing of plumbing material and tiles but following irregularities were noticed: Work Order: 27.03.2020 a. As per the quotation terms that supplier should be the authorized project dealer of the respective company, however, authorized project dealer certificate were not found on records from bidders- Party Name : Prashant Talekar / M R Gangani & Bros / Peace interiors | Medium | 85,812
MOC/20-21/0228 | 2020-09-07 | C112023546915 | 11 | Monetary | Procurement | Expression of Interest | M/s. Oswal Ceramics We observed that unit has made payment to Oswal Ceramics for purchasing of plumbing material and tiles but following irregularities were noticed: Work Order: 27.03.2020 a. As per the quotation terms that supplier should be the authorized project dealer of the respective company, however, authorized project dealer certificate were not found on records from bidders- Party Name : Prashant Talekar / M R Gangani & Bros / Peace interiors | Medium | 31917
B96 | 2021-02-01 | C032119800038 | 12 | Monetary | Procurement | Expression of Interest | Decospaa Interiors LLP (Vertical Blinds) We observed that payment has been made to Decospaa Interiors LLP for supply and installation of vertical blinds but following irregularities were noticed: Work order:27.03.2020 a. Quotation has been received from 1) Decospaa Interiors LLP 2) Shah Construction 3) Kala Builders.- b. As per the supply terms No. 3 before supply and installation the engineer or authorized representative from SMART office will inspect the quality of material in the godown of the vendor, however, inspection reports for the same was not made available to us for verification- c. Delivery challan was not made available to us for verification | Medium | 28600
B76 | 2020-10-21 | C112023587661 | 13 | Monetary | Procurement | Expression of Interest | Decospaa Interiors LLP (UPVC Window) We observed that unit has made payment to Decospaa Interiors LLP for purchasing of PVC window but following irregularities were noticed: Work Order: 27 March 2020. a. Quotation has been received from 1) Decospaa Interiors LLP 2) Themes Furnishing & Decore 3) Satori Consulting 4) S.P. Aluminium & Glass.- b. As per supply order terms No.1, It is required that technical expert of the supplier to visit the SMART office and take measurement and prepare actual required accessories and seek approval for the same from competent authority, however, copy of such measurement report was not made available to us for verification.- c. Supply should be made within 20 days from the date of order. | Medium | 270053
|  |  | 14 | Non - Monetary | Procurement | Discrepancies in compliance of procurement procedure | M/s. Shri Shivkripa Services. (Security services)- We had observed that payment has been made to M/s. Shri Shivkripa services for security services, however, following irregularities were noticed: a. Quotation received from 7 parties in which 3 parties are qualified for financial evaluation namely 1) Shivkrupa Services 2) Rakshak Security 3) OM Enterprices.- b. Envelopes, copy of quotation and other documents as per eligibility criteria of Rakshak security and OM Enterprises was not made available to us for verification.- c. As per quotation terms C (3), duly certified copies of satisfactory services for last three years shall be provided, however, only 2 year of duly certified copy of satisfactory services was made available to us for verification. d. As per quotation terms, Shivkrupa Services is required to make a security deposit of Rs. 50,000 however, no such proof of deposit like copy of DD or Cheque was made available to us for verification and receipt entry of security deposit was also not found in the accounting software. e. As per quotation terms no. J (5), agency is required to submit bio data, identity proof and address proof of the security guards duly verified but such document was not made available to us for verification. | Medium | 0
|  |  | 15 | Non - Monetary | Procurement | Expression of Interest | Ernst & Young LLP- We observed that payment was made to Ernst & Young LLP as consultancy to Development RFP for MIS and providing transaction advisory services for procurement of System Integrator to build digital MIS for the Department of Agriculture and SMART Project, however, following irregularities were noticed: a. Procurement documents, work order, minutes of meeting and approval from World Bank were not made available to us for verification. b. CV’s of the below mentioned experts does not match the criteria mentioned in agreement as on the date of agreement. Functional Business Analyst-Domain - Karishma Bhandara Experience required - >3, <=5yrs Actual Experience = 3 yrs)not >3 yrs) c. Penalty clause in case of non-submission of key deliverables or delay in deliverables is not mentioned in agreement | Medium | 0
|  |  | 16 | Non - Monetary | Procurement | Expression of Interest | Deloitte Touche Tohmatsu India LLP- We observed that payment was made to Deloitte Touche Tohmatsu India LLP for Study of constraints and development of strategy to promote exchange traded instruments for price risk mitigation by CBOs; however, following irregularities were noticed. a. Penalty clause in case of non-submission of key deliverables or delay in deliverables is not mentioned in agreement. b. Period of contract is 27.10.2020 to 23.02.2021, however, there is delay in deliverables c. Contract was extended for total 18 months till 31.08.2022 from the original contract, however, extension copy was not made available to us for verification. d. Technical evaluation Form IIIB and individual assessment sheet is not signed by the concerned authority. | High | 0
SS/Invoice/20-21/94 | 2020-10-09 | C102017414010 | 17 | Monetary | Admin | Deficiencies in record keeping | We have found deficiencies in proper documentation, record keeping, procurement details, supporting documents etc. The details of our observations are as follows: a. Unit has purchased from Sparkle Systems, however, quotation, delivery challan, stock book and other supporting documents were not made available to us for verification | Critical | 35200