## AuditPara
Audit Para Upload
Audit Ref. No. | SMART/2019-20/Int/0000 PCMU
Bill No | Bill Date (dd/mm/yyyy) | PFMS No. | Para No. | Audit Category (Monetary/Non-Monetary) | Audit Section (Procurement/Technical/Finance/MIS/Others) | Audit Para Title | Audit Description | Severity (Critical/High/Medium/Low) | Para Amount (in Rs.)
VAS/59/2019-20 | 2019-11-22 |  | 5 | Monetary | Procurement | Expression of Interest | M/s Vas Universal IT Solution- We had observed that payment has been made to M/s Vas Universal Solution for purchased of GIS desktop but following irregularities noticed: a. Quotation has been received from following: o Vas Universal IT Solution o Megabyte system o InfoWorld Technologies Pvt Ltd. b. Date of opening of envelopes is not mentioned on the envelopes and quotation of all the three parties. c. Inward stamp and received signature is missing on delivery challan. d. As per agreed terms, desktop should be delivered within 5 weeks from the date of award of contract, unit had given order on 21st September 2019, however, as per delivery challan, desktop was delivered to SMART office on 22nd November 2019 i.e. delay with 27 days. e. Installation report is not verified by concern person from SMART office. Details of payment is as follows: | Medium | 298540