## AuditPara
Audit Para Upload
Audit Ref. No. | SMART/2021-22/Int/0000 PCMU
Bill No | Bill Date (dd/mm/yyyy) | PFMS No. | Para No. | Audit Category (Monetary/Non-Monetary) | Audit Section (Procurement/Technical/Finance/MIS/Others) | Audit Para Title | Audit Description | Severity (Critical/High/Medium/Low) | Para Amount (in Rs.)
|  |  | 1 | Non - Monetary | Finance | Statutory Dues | TDS Short Deposited for the month of Apr-21: Rs. 100 ,May-21: Rs. 108700 ,Mar-22:Rs. 52,287 | Medium | 0
|  |  | 2 | Non - Monetary | Finance | Statutory Dues | GST Short Deposited for the month of Jun-21: Rs.600, Mar-22: 10458 | Medium | 0
|  |  | 3 | Non - Monetary | Procurement | Expression of Interest | d. As per office note sheet dated 06.10.2021 there is delay in submission of the following reports by Ernst & Young LLP Inception Report - 33days REoI & TOR - 39 days As Is Study Report - 34 days To be Study Report - 14 days Functional Requirement Specification (FRS) document - 25 days Detailed Project Report - 17 days Request for Proposal - 25 days | High | 0
B2074002407 | 2021-04-12 |  | 4 | Non - Monetary | Procurement | Expression of Interest | Deloitte Touche Tohmatsu India LLP- We observed that payment was made to Deloitte Touche Tohmatsu India LLP for Institutional and Functional Review to enhance institutional capacity for Agribusiness Reforms of Department of Agriculture (DOA) and Department of Marketing (DOM), Maharashtra State, however, following irregularities were noticed. a. Whitener is used to alter the date of the contract. b. Penalty clause in case of non-submission of key deliverables or delay in deliverables is not mentioned in agreement. c. Technical Proposals were opened on 16th October 2019 and the proposals was extended up to 07th may 2020, however, time extension letter, copy of minutes of meetings, technical & financial documents, bidder’s proposals, NOC from World Bank were not available for verification: d. Direct selection method of procurement is adopted. e. Period of contract is 23.09.2020 to 22.02.2021, however, there is delay in deliverables as follows: Inception Report - 241 days Interim Report - 208 days Integrated Draft Report - 259 days Integrated Final Report - 358 days f. As per letter no. PCMU/Fu.R/831/2021 dated 21.09.2021, Contract was extended for 2 months till 22.10.2021, therefore, revised timeline is required from Deloitte Touche Tohmatsu India LLP and the remaining deliverables to be completed till 22.10.2021, however, revised timelines were not achieved and the remaining deliverables were not completed in time. g. Contract was extended for total 8 months till 22.10.2021 from the original contract but extension copy is not provided to us for verification. | High | 667526
B463/21-22 | 2021-07-01 | C072109402008 | 5 | Monetary | Procurement | Expression of Interest | Shivkrupa Services (Housekeeping) We observed that unit has made payment to Shivkrupa Services for housekeeping, however, following irregularities were noticed: a. As per quotation terms No. 6 (a), selected agency is required to deposit Rs.50,000 either in the form of bank guarantee or DD within 10 days from the data of work order, however, work order was given on 22.10.2021 and DD for security deposit given by Shivkrupa services is on 22.06.2022. | High | 20567
B308/21-22 | 2021-06-01 | C062107773100 | 6 | Monetary | Procurement | Expression of Interest | Shivkrupa Services (Housekeeping) We observed that unit has made payment to Shivkrupa Services for housekeeping, however, following irregularities were noticed: a. As per quotation terms No. 6 (a), selected agency is required to deposit Rs.50,000 either in the form of bank guarantee or DD within 10 days from the data of work order, however, work order was given on 22.10.2021 and DD for security deposit given by Shivkrupa services is on 22.06.2022. | High | 20567
B160/21-22 | 2021-05-03 | C052132921041 | 7 | Monetary | Procurement | Expression of Interest | Shivkrupa Services (Housekeeping) We observed that unit has made payment to Shivkrupa Services for housekeeping, however, following irregularities were noticed: a. As per quotation terms No. 6 (a), selected agency is required to deposit Rs.50,000 either in the form of bank guarantee or DD within 10 days from the data of work order, however, work order was given on 22.10.2021 and DD for security deposit given by Shivkrupa services is on 22.06.2022. | High | 20567
B631/21-22 | 2021-08-02 | C082120353428 | 8 | Monetary | Procurement | Expression of Interest | Shivkrupa Services (Housekeeping) We observed that unit has made payment to Shivkrupa Services for housekeeping, however, following irregularities were noticed: a. As per quotation terms No. 6 (a), selected agency is required to deposit Rs.50,000 either in the form of bank guarantee or DD within 10 days from the data of work order, however, work order was given on 22.10.2021 and DD for security deposit given by Shivkrupa services is on 22.06.2022. | High | 20567
B1227/21-22 | 2021-11-01 | C112109820299 | 9 | Monetary | Procurement | Expression of Interest | Shivkrupa Services (Housekeeping) We observed that unit has made payment to Shivkrupa Services for housekeeping, however, following irregularities were noticed: a. As per quotation terms No. 6 (a), selected agency is required to deposit Rs.50,000 either in the form of bank guarantee or DD within 10 days from the data of work order, however, work order was given on 22.10.2021 and DD for security deposit given by Shivkrupa services is on 22.06.2022. | High | 20567
B1349/21-22 | 2021-12-01 | C122123812632 | 10 | Monetary | Procurement | Expression of Interest | Shivkrupa Services (Housekeeping) We observed that unit has made payment to Shivkrupa Services for housekeeping, however, following irregularities were noticed: a. As per quotation terms No. 6 (a), selected agency is required to deposit Rs.50,000 either in the form of bank guarantee or DD within 10 days from the data of work order, however, work order was given on 22.10.2021 and DD for security deposit given by Shivkrupa services is on 22.06.2022. | High | 20567
B1545/21-22 | 2022-01-01 | C012234395801 | 11 | Monetary | Procurement | Expression of Interest | Shivkrupa Services (Housekeeping) We observed that unit has made payment to Shivkrupa Services for housekeeping, however, following irregularities were noticed: a. As per quotation terms No. 6 (a), selected agency is required to deposit Rs.50,000 either in the form of bank guarantee or DD within 10 days from the data of work order, however, work order was given on 22.10.2021 and DD for security deposit given by Shivkrupa services is on 22.06.2022. | High | 20567