## AuditPara
Audit Para Upload
Audit Ref. No. | SMART/2022-23/Int/0800 PIUMSR
Bill No | Bill Date (dd/mm/yyyy) | PFMS No. | Para No. | Audit Category (Monetary/Non-Monetary) | Audit Section (Procurement/Technical/Finance/MIS/Others) | Audit Para Title | Audit Description | Severity (Critical/High/Medium/Low) | Para Amount (in Rs.)
|  |  | 1 | Non - Monetary | Finance | Non-availability of statutory challans | Challans of statutory dues paid by the unit were not made available for our verification. | High | 0
B71 | 2022-02-15 | C042252422932 | 2 | Monetary | Procurement | Discrepancies in compliance of record keeping in tranche to CBOs | Primove Infrastructure Development Consultants Pvt. Ltd. Payment has been made to Primove Infrastructure Development Consultants Pvt. Ltd. for bridge technical support services to CLFs and CMRCs Package 1 Vidarbha and Marathwada Region, however, following irregularities were noticed: 1) Original Agreement and documents are available with Smart office. 2) Penalty clause is not inserted in the agreement. 3) The period of contract is from 27.12.2021 to 27.12.2023 and as per agreement, payment should be made as follows: • 5% payment should be made on the basis of submission of inception report & resource mobilization within 0-1 month, however, the date of submission of inception report is 15.02.2022 (with a delay of 30 days). Also no action has been taken by the unit. • 5% payment should be made on the basis of report of baseline survey mapping of potential CLFs and CMRCs and awareness campaigns within 2-3 months, however, the date of submission of Baseline Survey mapping report is 16.04.2022 (with a delay of 30 days). Also no action has been taken by the unit. • 5% payment should be made on the basis of report of orientation program carried out for mobilization of FPCs from CLFs and CMRCs within 3-4 months, however, the date of submission of Orientation Program Mobilization report is 16.06.2022 (with a delay of 60 days). Also no action has been taken by the unit. | High | 0
B01 | 2022-04-18 | C062208227463 | 3 | Monetary | Procurement | Discrepancies in compliance of record keeping in tranche to CBOs | Primove Infrastructure Development Consultants Pvt. Ltd. Payment has been made to Primove Infrastructure Development Consultants Pvt. Ltd. for bridge technical support services to CLFs and CMRCs Package 1 Vidarbha and Marathwada Region, however, following irregularities were noticed: 1) Original Agreement and documents are available with Smart office. 2) Penalty clause is not inserted in the agreement. 3) The period of contract is from 27.12.2021 to 27.12.2023 and as per agreement, payment should be made as follows: • 5% payment should be made on the basis of submission of inception report & resource mobilization within 0-1 month, however, the date of submission of inception report is 15.02.2022 (with a delay of 30 days). Also no action has been taken by the unit. • 5% payment should be made on the basis of report of baseline survey mapping of potential CLFs and CMRCs and awareness campaigns within 2-3 months, however, the date of submission of Baseline Survey mapping report is 16.04.2022 (with a delay of 30 days). Also no action has been taken by the unit. • 5% payment should be made on the basis of report of orientation program carried out for mobilization of FPCs from CLFs and CMRCs within 3-4 months, however, the date of submission of Orientation Program Mobilization report is 16.06.2022 (with a delay of 60 days). Also no action has been taken by the unit. | High | 0
B25 | 2022-06-17 | C072239963353 | 4 | Monetary | Procurement | Discrepancies in compliance of record keeping in tranche to CBOs | Primove Infrastructure Development Consultants Pvt. Ltd. Payment has been made to Primove Infrastructure Development Consultants Pvt. Ltd. for bridge technical support services to CLFs and CMRCs Package 1 Vidarbha and Marathwada Region, however, following irregularities were noticed: 1) Original Agreement and documents are available with Smart office. 2) Penalty clause is not inserted in the agreement. 3) The period of contract is from 27.12.2021 to 27.12.2023 and as per agreement, payment should be made as follows: • 5% payment should be made on the basis of submission of inception report & resource mobilization within 0-1 month, however, the date of submission of inception report is 15.02.2022 (with a delay of 30 days). Also no action has been taken by the unit. • 5% payment should be made on the basis of report of baseline survey mapping of potential CLFs and CMRCs and awareness campaigns within 2-3 months, however, the date of submission of Baseline Survey mapping report is 16.04.2022 (with a delay of 30 days). Also no action has been taken by the unit. • 5% payment should be made on the basis of report of orientation program carried out for mobilization of FPCs from CLFs and CMRCs within 3-4 months, however, the date of submission of Orientation Program Mobilization report is 16.06.2022 (with a delay of 60 days). Also no action has been taken by the unit. | High | 0
MH/01/2022-23 | 2022-05-11 | C062221957085 | 5 | Monetary | Procurement | Discrepancies in compliance of record keeping in tranche to CBOs | Bhartiya Samruddhi Investments and Consulting Services Ltd. (BASIX) Payment has been made to Bhartiya Samruddhi Investments and Consulting Services Ltd. (BASIX) for bridge technical support services to CLFs and CMRCs Package 2 North Maharashtra Konkan & Western Region, however, following irregularities were noticed: 1) Original Agreement and documents were not made available for our verification. 2) Penalty clause is not inserted in the agreement. 3) The period of contract is from 16.03.2022 to 16.03.2024 and as per the agreement, 5% payment should be made on the basis of submission of inception report & resource mobilization within 0-1 month, however, inception report, resource mobilization report and date of submission of reports were not made available to us for verification. | High | 0
|  |  | 6 | Monetary | Procurement | Discrepancies in compliance of record keeping in tranche to CBOs | Jivanonnati Women Farmer Producer Co. Ltd. Payment has been made to Jivanonnati Women Farmer Producer Co. Ltd. (Jivanonnati Mahila Shetkari Utpadak Co. Ltd.) for warehousing services as first tranche of project grants, however, following irregularities were noticed: 1) Original Memorandum of Understanding between Jivanonnati Women Farmer Producer Co. Ltd. and Arya Collateral Warehousing Services Ltd. on Rs 500 stamp paper was not made available to us for verification. 2) The indicative standing instructions is not mentioned in the agreement between Jivanonnati Women Farmer Producer Co Ltd. and PIU MSRLM - “CBO shall not issue payments to sister concerns/directors/officials for activities mentioned in the proposal, subject to they should be selected through the competitive process/procurement process prescribed by Project”. 3) As per FMM manual dated 14th Nov 2019, authorised signatories of the CBO shall be mentioned in the grant agreement, however, the same is missing in the agreement. 4) PIU has released the 1st Tranche to CBO without fulfilling a condition of 40% beneficiary contribution by CBO since Rs. 21,02,966.70 was deposited by CBO instead of Rs 40,54,000 at the time of submission of demand letter for 1st Tranche. 5) The following documents were not made available to us for verification. • Hiring of tally literate person/CA/CA firm for accounting by the CBO • Declaration by CBO for purchase of tally accounting /other double entry software related by the CBO • Approval of cost estimates by in house technical person at PCMU/related line department • Opening of dedicated bank account for SMART by CBO and • Deposit of beneficiary share • Copy of demand letter by CBO. • Copy of recommendation letter by respective PIU | High | 0
MH/03/2022-23 | 2022-07-08 | C082221934344 | 7 | Monetary | Procurement | Discrepancies in compliance of record keeping in tranche to CBOs | Bhartiya Samruddhi Investments and Consulting Services Ltd (BASIX) We observed that payment has been made to Bhartiya Samruddhi Investments and Consulting Services Ltd (BASIX) for bridge technical support services to CLFs and CMRCs Package 2 North Maharashtra Konkan & Western Region, however, following irregularities were noticed: a. Original Agreement, documents, TDS challan of Rs.2,94,839 and return were not made available to us for our verification. b. The period of contract is from 16.03.2022 to 16.03.2024 and as per the agreement, 5% payment should be made on the basis of report of baseline survey mapping of potential CLFs and CMRCs and awareness campaigns within 2-3 months, however, the date of submission of report is 8th July 2022 (with a delay of 15 days). | High | 0
|  | C082261902642 | 8 | Monetary | Procurement | Incomplete and Improper Maintenance of records | It was observed that payment was made towards salary to Ms. Sharmila Jadhav for May,June, July & August 2022, however, Professional tax and TDS challan copy was not made available for our verification. | Medium | 0
|  | C0822213866641 | 9 | Monetary | Procurement | Incomplete and Improper Maintenance of records | It was observed that payment was made towards salary to Ms. Sharmila Jadhav for May,June, July & August 2022, however, Professional tax and TDS challan copy was not made available for our verification. | Medium | 0
Proforma Invoice no. 65 | 2022-09-16 | C112207937755 | 10 | Non - Monetary | Procurement | Incomplete and Improper Maintenance of records | PRIMOVE INFRASTRUCTURE DEVELOPMENT PVT LTD. Payment has been made to PRIMOVE INFRASTRUCTURE DEVELOPMENT PVT LTD. and Consulting Services Ltd for bridge technical support services to CLFs and CMRCs Package 1 Vidharba & Marathwada Region(19 District), however, following irregularities were noticed: The period of contract is from 27.12.2021 to 27.12.2023 and as per the agreement, 5% payment should be made on the basis of report of baseline survey mapping of potential CLFs and CMRCs and awareness campaigns within 2-3 months, however, the date of submission of report were not made available to us for verification. | Medium | 0
MH/04/2022-23 | 2022-09-21 | C112206302057 | 11 | Non - Monetary | Procurement | Incomplete and Improper Maintenance of records | Bhartiya Samruddhi Investments and Consulting Services Ltd (BASIX) Payment has been made to Bhartiya Samruddhi Investments and Consulting Services Ltd (BASIX) for bridge technical support services to CLFs and CMRCs Package 2 North Maharashtra Konkan & Western Region, however, following irregularities were noticed: The period of contract is from 16.03.2022 to 16.03.2024 and as per the agreement, 5% payment should be made on the basis of report of baseline survey mapping of potential CLFs and CMRCs and awareness campaigns within 2-3 months, however, the date of submission of report were not made available to us for verification. | High | 0