## AuditPara
Audit Para Upload
Audit Ref. No. | SMART/2021-22/Int/0100 PIUAG
Bill No | Bill Date (dd/mm/yyyy) | PFMS No. | Para No. | Audit Category (Monetary/Non-Monetary) | Audit Section (Procurement/Technical/Finance/MIS/Others) | Audit Para Title | Audit Description | Severity (Critical/High/Medium/Low) | Para Amount (in Rs.)
|  |  | 1 | Non - Monetary | Finance | Incomplete and Improper Maintenance of records | a. Expense vouchers are not recorded sequentially. b. Physical copy of voucher number and date are not reconciled with the tally vouchers. | Medium | 0
|  |  | 2 | Non - Monetary | Procurement | Discrepancies in compliance of procurement procedure and record keeping | Grushneshwar PCL, Abad (CBO) Unit has made payment to Grushneshwar PCL, Abad (CBO), however, following irregularities were noticed: a. CBO is required to open a bank account in the name of “SMART-Name of the CBO”, however, CBO opened the bank in the name of CBO itself without the word “SMART”. b. SPAC committee gave approval on 08.05.2020 for Rs.107.03 Lakhs which was revised on 15.06.2021 for Rs.82.29 lakhs, however, grant agreement was executed on 29.01.2021 and revised grant agreement was not made available for our verification. c. Date is not mentioned in the demand letter received from CBO for disbursement of tranches. d. Name of the 2 authorized signatories and contact details of the CBO and PIU were not mentioned in the grant agreement executed between both the parties. e. As per SPAC committee letter, CBO is required to submit loan sanctioned letter/copy of passbook for self-contribution and MOU with CMA within 60 days of approval by the committee, however, SPAC committee gave approval on 08.05.2020 whereas grant agreement was executed on 29.01.2021 (with a delay of 205 days) and amount was deposited by CBO on 18.03.2021 (with a delay of 253 days). | Medium | 0
|  |  | 3 | Non - Monetary | Procurement | Discrepancies in compliance of procurement procedure and record keeping | Krishi Kranti Hitech PCL, Abad (CBO) Unit has made payment to Krishi Kranti Hitech PCL, Abad (CBO), however, following irregularities were noticed: a. As per SPAC committee letter, CBO is required to submit loan sanctioned letter/copy of passbook for self-contribution and MOU with CMA within 60 days of approval by the committee, however, the SPAC committee gave approval on 08.05.2020 whereas grant agreement was executed on 21.01.2021 (with a delay of 197 days) amount was deposited by CBO on 05.02.2021 (with a delay of 212 days). b. Name of the 2 authorized signatories and contact details of the CBO and PIU were not mentioned in the grant agreement executed for disbursing tranche to CBO. c. Date of execution of agreement and date of completion of agreement is same as per the grant agreement i.e., 29.01.2021. | Medium | 0
|  |  | 4 | Non - Monetary | Procurement | Discrepancies in compliance of procurement procedure and record keeping | Lokmauli Agro PCL, Latur (CBO) Unit has made payment to Lokmauli Agro PCL, Latur (CBO), however, following irregularities were noticed: a. Name of the 2 authorized signatories, contact details of authorized representative of grant provider, date of execution and completion of agreement were not mentioned in the grant agreement executed for disbursing tranche to CBO. b. As per SPAC committee letter, CBO is required to submit loan sanctioned letter/copy of passbook for self-contribution and MOU with CMA within 60 days of approval by the committee, however, SPAC committee gave approval on 08.05.2020 whereas amount was deposited by CBO on 25.03.2021 (with a delay of 260 days) c. Grant agreement executed for disbursing tranche to CBO is not signed by PIU authorized officer. | Medium | 0
|  |  | 5 | Non - Monetary | Procurement | Discrepancies in compliance of procurement procedure and record keeping | Aroma Organic Agro PCL, Latur (CBO) Unit has made payment to Aroma Organic Agro PCL, Latur (CBO), however, following irregularities were noticed: a. Grant agreement executed for disbursing tranche to CBO is not signed by PIU authorized officer. b. Contact details of authorized representative of grant provider were not mentioned in the grant agreement. c. As per SPAC committee letter, CBO is required to submit loan sanctioned letter/copy of passbook for self-contribution and MOU with CMA within 60 days of approval by the committee, however, SPAC committee gave approval on 08.05.2020 whereas grant agreement was executed on 15.01.2020 (with a delay of 191 days) and amount was deposited by CBO on 19.03.2021 (with a delay of 253 days). d. Dated photograph of first RA bill and invoice of advertisement expenses were not made available to us for verification. e. As per agreement of CBO with Ashirwad Construction 1st RA bill should be raised for 25% of the total contract price i.e.Rs.37,45,744, however, the bill raised was of Rs.59,72,494.3 i.e., 39.86% that was paid by the CBO. | Medium | 0
| 2021-07-26 |  | 6 | Non - Monetary | Procurement | Discrepancies in compliance of procurement procedure and record keeping | Vikas Agro PCL Latur Payment was made to Vikas Agro PCL Latur for productive partnership proposal as first & second tranche of project grants, however, following irregularities were noticed: Contractor details- Shriram Construction Latur a. Original Articles of Agreement between Vikas Agro PCL Latur and Shriram Construction Latur was not made to us for verification. b. Original Agreement between Vikas Agro PCL Latur and PIU was not made to us for verification. c. Original Memorandum of Understanding between Vikas Agro PCL Latur and ADM Agro Industries Latur and Vizag Pvt Ltd was not made to us for verification. d. Date of execution and period was not mentioned in the grant agreement executed for disbursing tranche to CBO between Vikas Agro PCL Latur and PIU Agriculture. e. As per FMM manual dated 14th Nov 2019, the authorised signatories of CBO shall be mentioned in the grant agreement, however, the same is missing in the agreement between Vikas Agro PCL Latur and PIU Agriculture. f. The indicative standing instructions is not mentioned in the agreement between Vikas Agro PCL Latur and PIU agriculture - “CBO shall not issue payments to sister concerns/directors/officials for activities mentioned in the proposal, subject to they should be selected through the competitive process/procurement process prescribed by Project”. g. Date was not mentioned in the geo tagged photos and photograph attached for 1st RA Bill. h. Photograph for 2nd RA Bill and copy of recommendation letter by respective PIU was not provided to us for verification. i. Name of the 2 authorized signatories and authorized representative of grant provider was not mentioned in the grant agreement. j. Inspection Report is not signed by an Accountant. k. As per FMM manual dated 14th Nov 2019, on receipt of demand from CBO, PIU shall release the 1st Tranche within 7 working days, however, demand letter from CBO to disburse tranche is dated 17.03.2021 whereas the PIU has released 1st Tranche on 26.07.2021 (with a delay of 122 days). l. As per FMM manual dated 14th Nov 2019, on receipt of demand from CBO, PIU shall release the 2nd Tranche within 7 working days, however, demand letter from CBO to disburse tranche is dated 01.12.2021 whereas PIU has released 2nd Tranche on 23.02.2022 (with a delay of 77 days). | High | 61,20,000
| 2022-02-23 |  | 7 | Non - Monetary | Procurement | Discrepancies in compliance of procurement procedure and record keeping | Vikas Agro PCL Latur Payment was made to Vikas Agro PCL Latur for productive partnership proposal as first & second tranche of project grants, however, following irregularities were noticed: Contractor details- Shriram Construction Latur a. Original Articles of Agreement between Vikas Agro PCL Latur and Shriram Construction Latur was not made to us for verification. b. Original Agreement between Vikas Agro PCL Latur and PIU was not made to us for verification. c. Original Memorandum of Understanding between Vikas Agro PCL Latur and ADM Agro Industries Latur and Vizag Pvt Ltd was not made to us for verification. d. Date of execution and period was not mentioned in the grant agreement executed for disbursing tranche to CBO between Vikas Agro PCL Latur and PIU Agriculture. e. As per FMM manual dated 14th Nov 2019, the authorised signatories of CBO shall be mentioned in the grant agreement, however, the same is missing in the agreement between Vikas Agro PCL Latur and PIU Agriculture. f. The indicative standing instructions is not mentioned in the agreement between Vikas Agro PCL Latur and PIU agriculture - “CBO shall not issue payments to sister concerns/directors/officials for activities mentioned in the proposal, subject to they should be selected through the competitive process/procurement process prescribed by Project”. g. Date was not mentioned in the geo tagged photos and photograph attached for 1st RA Bill. h. Photograph for 2nd RA Bill and copy of recommendation letter by respective PIU was not provided to us for verification. i. Name of the 2 authorized signatories and authorized representative of grant provider was not mentioned in the grant agreement. j. Inspection Report is not signed by an Accountant. k. As per FMM manual dated 14th Nov 2019, on receipt of demand from CBO, PIU shall release the 1st Tranche within 7 working days, however, demand letter from CBO to disburse tranche is dated 17.03.2021 whereas the PIU has released 1st Tranche on 26.07.2021 (with a delay of 122 days). l. As per FMM manual dated 14th Nov 2019, on receipt of demand from CBO, PIU shall release the 2nd Tranche within 7 working days, however, demand letter from CBO to disburse tranche is dated 01.12.2021 whereas PIU has released 2nd Tranche on 23.02.2022 (with a delay of 77 days). | High | 3660000
|  |  | 8 | Non - Monetary | Procurement | Discrepancies in compliance of procurement procedure and record keeping | Katpur Agro Producer Company Ltd Payment was made to Katpur Agro Producer Company Ltd for productive partnership proposal as first & second tranche of project grants, however, following irregularities were noticed: Contractor details- Dhanchandra Construction. a. Original Articles of Agreement between Katpur Agro Producer Company Ltd and Dhanchandra Construction was not made available to us for verification. b. Original Memorandum of Understanding between Katpur Agro Producer Company Ltd and ADM Agro Industries Latur and Vizag Pvt Ltd was not made available to us for verification. c. Date of execution and period was not mentioned in the grant agreement executed for disbursing tranche to CBO between Katpur Agro Producer Company Ltd and PIU Agriculture. d. As per FMM manual dated 14th Nov 2019, the authorised signatories of CBO will be mentioned in the grant agreement, however, the same is missing from the agreement between Katpur Agro Producer Company Ltd and PIU Agriculture. e. The indicative standing instructions is not mentioned in the agreement between Katpur Agro Producer Company Ltd and PIU agriculture - “CBO shall not issue payments to sister concerns/directors/officials for activities mentioned in the proposal, subject to they should be selected through the competitive process/procurement process prescribed by Project”. f. Name of the 2 authorized signatories and authorized representative of grant provider was not mentioned in the grant agreement. g. Copy of recommendation letter by PIU was not made available to us for verification. h. Inspection Report was not signed by an Accountant. i. As per FMM manual dated 14th Nov 2019, on receipt of demand from CBO, PIU shall release the 1st Tranche within 7 working days, however, demand letter from CBO to disburse tranche is dated 17.03.2021 whereas PIU has released 1st Tranche dated 26.07.2021 (with a delay of 122 days). j. As per FMM manual dated 14th Nov 2019, on receipt of demand from CBO, PIU shall release the 2nd Tranche within 7 working days, however, demand letter from CBO to disburse tranche is dated 01.12.2021 whereas PIU has released 2nd Tranche dated 23.02.2022 (with a delay of 77 days). | High | 61,20,000
|  |  | 9 | Non - Monetary | Procurement | Discrepancies in compliance of procurement procedure and record keeping | Katpur Agro Producer Company Ltd Payment was made to Katpur Agro Producer Company Ltd for productive partnership proposal as first & second tranche of project grants, however, following irregularities were noticed: Contractor details- Dhanchandra Construction. a. Original Articles of Agreement between Katpur Agro Producer Company Ltd and Dhanchandra Construction was not made available to us for verification. b. Original Memorandum of Understanding between Katpur Agro Producer Company Ltd and ADM Agro Industries Latur and Vizag Pvt Ltd was not made available to us for verification. c. Date of execution and period was not mentioned in the grant agreement executed for disbursing tranche to CBO between Katpur Agro Producer Company Ltd and PIU Agriculture. d. As per FMM manual dated 14th Nov 2019, the authorised signatories of CBO will be mentioned in the grant agreement, however, the same is missing from the agreement between Katpur Agro Producer Company Ltd and PIU Agriculture. e. The indicative standing instructions is not mentioned in the agreement between Katpur Agro Producer Company Ltd and PIU agriculture - “CBO shall not issue payments to sister concerns/directors/officials for activities mentioned in the proposal, subject to they should be selected through the competitive process/procurement process prescribed by Project”. f. Name of the 2 authorized signatories and authorized representative of grant provider was not mentioned in the grant agreement. g. Copy of recommendation letter by PIU was not made available to us for verification. h. Inspection Report was not signed by an Accountant. i. As per FMM manual dated 14th Nov 2019, on receipt of demand from CBO, PIU shall release the 1st Tranche within 7 working days, however, demand letter from CBO to disburse tranche is dated 17.03.2021 whereas PIU has released 1st Tranche dated 26.07.2021 (with a delay of 122 days). j. As per FMM manual dated 14th Nov 2019, on receipt of demand from CBO, PIU shall release the 2nd Tranche within 7 working days, however, demand letter from CBO to disburse tranche is dated 01.12.2021 whereas PIU has released 2nd Tranche dated 23.02.2022 (with a delay of 77 days). | High | 36,60,000