## AuditPara
Audit Para Upload
Audit Ref. No. | SMART/2024-25/Int/0154 VAN0154 VAN/Q3
Bill No | Bill Date (yyyy-MM-dd) | PFMS No. | Para No. | Audit Category (Monetary/Non-Monetary) | Audit Section (Procurement/Technical/Finance/MIS/Others) | Audit Para Title | Audit Description | Severity (Critical/High/Medium/Low) | Para Amount (in Rs.)
NA | 2025-03-31 | NA | 1 | Monetary | Finance | Delay in documentation | It has been observed that secondary books of accounts such as Cheque Issue/Bank Draft Issue Register, Advance Register, Security Deposit Register, Beneficiary Contribution Register, Fixed Asset Register/Dead Stock Register and Imprest Amount Register are not being updated till March 31, 2025 as per the Format prescribed under Financial Management Manual. 1. Cheque issue / bank draft issue register. 2.Advance Register 3.Security Deposit Register 4. Beneficiary Contribution Register 5. Fixed Asset/ Dead Stock register 6. Imprest Amount Register | Low | NA
NA | 2025-02-07 | C012551641645 | 2 | Monetary | Finance | Delay in documentation | We Observed that payment has been made to RAMETI (Rural Agriculture Extension Management Training Institute) for CBO Smart Training, but Training Order and Training plan copy, Utilization Certificate were not provided to us for audit verification. Date of payment 31-03-2025 of Rs.1696500 | Medium | 1696500
NA | 2025-03-31 | NA | 3 | Monetary | Finance | Delay in documentation | It was observed that there was a difference of Rs. 150000/- between the grant receipt and expenditure reported in the Books of Accounts and the IUFR for Q3 (FY 2024-25). Further, it was noted that there was a misclassification in the Received grants, specifically under the Components D, G. 1.Budgetary Grants/ Grants Received Date of payment 31-03-2025 of Rs. 150000 | High | 150000
NA | 2025-03-31 | NA | 4 | Monetary | Finance | Delay in documentation | It was observed that there was a difference amounting to Rs. 150000/- between the amount reported as per the utilization certificate and that reported as per the books of accounts. Date of payment 31-03-2025 of Rs. 150000 | High | 150000