## Summary
GoM
Sr.No | Name of IT System / Activity | Sub-Component / Sub-Modules
In Processs - API Request raised
1 | MahaDBT | Farm Mechanization > RKVY | Inprogress
Farm Mechanization > NFSM
Farm Mechanization > SMAM
Horticulture > MIDH > Area Expansion
Horticulture > MIDH > Post Harvest Mangement.
Horticulture > MIDH > Community Tank
Irrigation > PMKSY > Drip Irrigation
SC/ST Scheme
2 | Cropwatch
3 | Crop Pest Surveillance and Advisory Project (Crop SAP)
4 | e-Parwana (Mahaonline Ltd.)
5 | Rainfall Recording & Analysis
In Development Phase
6 | MahaAGRITECH |  | On Hold
7 | E - Lab Seed Software |  | On Hold
8 | E - Lab Fertilizer Software |  | On Hold
9 | E - Lab Pesticide Software |  | On Hold
Obselete
10 | Advance Yield Estimation |  | Closed
11 | e-Parwana (NIC Pune) |  | Closed
12 | e-Thibak |  | Closed
Offline
13 | Agricultural Technology Management Agency (ATMA)
14 | Horticulture |  | Inprogress
15 | Statistics
16 | National Horticulture Mission (NHM) |  | Inprogress
17 | Input and Quality Control (IQC)
18 | Soil Lab 3.0 |  | Inprogress
19 | Organic Farming Mission
In Progress
20 | Farm Field School app (FFS)-PoCRA | PoCRA team will provide common link for all application | Completed
21 | Finance Information Management System (FIMS)-PoCRA
22 | GIS Platform - PoCRA
23 | PoCRA Micro Level Planning App
24 | Staff Monitoring app (SMA)-PoCRA
25 | Team MahaPoCRA - Single Sign on system
26 | PoCRA Training App
27 | DBT-PoCRA
28 | Water Budget Model - PoCRA
On hold
29 | Maha Cott |  | On Hold
Legends Used
In Development Phase
Offline Applications
Obselete
On Hold

## GoM
Application Details |  |  | Requirement gathering |  |  |  | Data collection through APIs |  |  | Development |  |  |  | SPOC
Sr.No | Name of IT System / Activity | Sub-Component / Sub-Modules | Requirement Discussion | Data Field Identification | Requirement document with wireframe shared with client? | Client sign off on document? | Communication regarding sharing data / API done? | Date on which letter has been issued / communication date / Follow-up date | Data / API received from client / concerned party? | Development started? | Conducted UAT | Post UAT changes and sign off on UAT | Release on production for departmental users | Concern Person Name | Concern Person Contact details | Concern Person E mail Id
|  |  | Pending / Completed / Not yet started | Pending / Completed / Not yet started | Yes / No | Received / Pending / Working on changes suggested | Yes / No | dd-mmm-yyyy <add remark against each date> | Yes / No | Yes / No | Yes / No | Pending / Completed | Pending / Completed
1 | MahaDBT | Farm Mechanization > RKVY | Completed | Completed | Yes | Received (refer to MOM dated dd-mmm-yyyy) | Yes | 2023-04-01 | No | No | No | Pending | Pending | Mr. Kantilal Pawar
|  | Farm Mechanization > NFSM | Completed | Completed | Yes | Received | Yes |  | No | No | No | Pending | Pending
|  | Farm Mechanization > SMAM | Completed | Completed | Yes | Received | Yes |  | No | No | No | Pending | Pending
|  | Horticulture > MIDH > Area Expansion | Completed | Completed | Yes | Received | Yes |  | No | No | No | Pending | Pending
|  | Horticulture > MIDH > Post Harvest Mangement. | Completed | Completed | Yes | Received | Yes |  | No | No | No | Pending | Pending
|  | Horticulture > MIDH > Community Tank | Completed | Completed | Yes | Received | Yes |  | No | No | No | Pending | Pending
|  | Irrigation > PMKSY > Drip Irrigation | Completed | Completed | Yes | Received | Yes |  | No | No | No | Pending | Pending
|  | SC/ST Scheme | Completed | Completed | Yes | Received | Yes |  | No | No | No | Pending | Pending
2 | Rainfall Recording & Analysis |  | Completed | Completed | Yes | Received | Yes | 2023-04-01 | Yes | No | No | Pending | Pending | Hiremath Sir | 9765618864 | ddastat2@gmail.com
3 | Cropwatch |  | Completed | Completed | Yes | Received | Yes | 2023-04-01 | No | No | No | Pending | Pending
4 | Crop Pest Surveillance and Advisory Project (Crop SAP) |  | Completed | Completed | Yes | Received | Yes | 2023-04-01 | No | No | No | Pending | Pending
5 | e-Parwana (Mahaonline Ltd.) |  | Completed | Completed | Yes | Pending | No |  | No | No | No | Pending | Pending
6 | PoCRA | Farm Field School app (FFS) | Completed | Completed | No |  | No |  | No | In Progress | No | Pending | Pending | Mr. Vijay Kolekar
|  | Finance Information Management System (FIMS) | Completed | Completed | No |  | No |  | No | In Progress | No | Pending | Pending | Mr. Vijay Kolekar
|  | GIS Platform | Completed | Completed | No |  | No |  | No | In Progress | No | Pending | Pending | Mr. Vijay Kolekar
|  | Micro Level Planning App | Completed | Completed | No |  | No |  | No | In Progress | No | Pending | Pending | Mr. Vijay Kolekar
|  | Staff Monitoring app (SMA) | Completed | Completed | No |  | No |  | No | In Progress | No | Pending | Pending | Mr. Vijay Kolekar
|  | Single Sign-on system | Completed | Completed | No |  | No |  | No | In Progress | No | Pending | Pending | Mr. Vijay Kolekar
|  | Training App | Completed | Completed | No |  | No |  | No | In Progress | No | Pending | Pending | Mr. Vijay Kolekar
|  | DBT | Completed | Completed | No |  | No |  | No | In Progress | No | Pending | Pending | Mr. Vijay Kolekar
|  | Water Budget Model | Completed | Completed | No |  | No |  | No | In Progress | No | Pending | Pending | Mr. Vijay Kolekar
7 | Soil Lab 3.0 |  | In Progress | Completed | No |  | No |  | No | In Progress | No | Pending | Pending | Mr. Ravindra Wadkar | 9404953873 | soilpune@gmail.com raviwadkar@gmail.com
8 | Organic Farming Mission |  | In Progress | Completed | [9 empty] | Mr. Arif Shah | 9422508086 | pdorganicfarmingmission@gmail.com
9 | Horticulture | Bhausaheb Fundkar Phalbaag Lagvad Yojana | Completed | Completed | No |  | No |  | No | No | No | Pending | Pending | Mr. Kailash Mote
|  | Horticulture plantation report-MREGS | Completed | Completed
|  | Horticulture nursery -Availability report | In Progress | Pending
|  | Plantation of fruits trees and vegetables in the backyard of SC house | Completed | Completed
10 | Statistics |  | Inprogress | Pending | Yes |  | No |  | No | No | No | Pending | Pending
11 | National Horticulture Mission (NHM) |  | In Progress | Pending | No |  | No |  | No | No | No | Pending | Pending | Mr. Kailash Mote
12 | Input and Quality Control (IQC) |  | Not Yet Started | Pending | No |  | No |  | No | No | No | Pending | Pending
13 | E - Lab Seed Software |  | In Development Phase | Completed | On Hold |  | No |  | No | No | No | Pending | Pending | Mr. Sunil Borkar
14 | E - Lab Fertilizer Software |  | In Development Phase | Completed | On Hold |  | No |  | No | No | No | Pending | Pending | Mr. Sunil Borkar
15 | E - Lab Pesticide Software |  | In Development Phase | Completed | On Hold |  | No |  | No | No | No | Pending | Pending | Mr. Sunil Borkar
16 | MahaAGRITECH |  | In Development Phase | Completed | On Hold |  | No |  | No | No | No | Pending | Pending
17 | Agricultural Technology Management Agency (ATMA) |  | In Development Phase |  |  |  | No |  | No | No | No | Pending | Pending | Mr. Dashrath Tambole
18 | Maha Cott |  | On Hold | On Hold | On Hold |  | No |  | No | No | No | Pending | Pending | Mr. Jayesh Mahajan | 82755133783 | jayeshpmahajan@gmail.com
19 | Advance Yield Estimation |  | Obselete | Completed | No | NA | NA | NA | NA | NA | NA | NA | NA
20 | e-Parwana (NIC Pune) |  | Obselete | Completed | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
21 | e-Thibak |  | Obselete | Completed | NA | NA | NA | NA | NA | NA | NA | NA | NA | Mr. Kantilal Pawar
Legends Used
|  | In Development Phase | Application is in development phase
|  | Offline Applications | Workflow is carried out offline. Data is getting captured in excel sheet.
|  | Obselete | Applications are not in used.
|  | On Hold | Yet to be decided if Integration is needed.

## GoI
Application Details |  |  | Requirement gathering |  |  |  | Data collection thorugh APIs |  |  | Development |  |  |  | SPOC
Sr.No | Name of IT System / Activity | Sub-Component / Sub-Modules | Requirement Discussion | Data Field Identification | Requirement document with wireframe shared with client? | Client sign off on document? | Communication regarding sharing data / API done? | Date on which letter has been issued / communication date / Follow-up date | Data / API received from client / concerned party? | Development started? | Conducted UAT | Post UAT changes and sign off on UAT | Release on production for departmental users | Concern Person Name | Concern Person Contact details | Concern Person E mail Id
|  |  | Pending / Completed / Not yet started | Pending / Completed / Not yet started | Yes / No | Received / Pending / Working on changes suggested | Yes / No | dd-mmm-yyyy <add remark against each date> | Yes / No | Yes / No | Yes / No | Pending / Completed | Pending / Completed
1 | Issue Of Grower Certificate For Import Of Planting Material |  | Not Started | Completed | No |  | Yes | 21/03/2023 | No | No | No | Pending | Pending
2 | Nursery License |  | Not Started | Completed | No |  | Yes |  | No | No | No | Pending | Pending
3 | Pradhan Mantri Fasal Bima Yojna |  | Not Started | Completed | No |  | Yes | 21/03/2023 | No | No | No | Pending | Pending
4 | Weather based Crop Insurance |  | Not Started | Completed | No |  | Yes | 21/03/2023 | No | No | No | Pending | Pending
5 | Integrated Fertilizer Management System |  | Not Started | Completed | No |  | Yes | 21/03/2023 | No | No | No | Pending | Pending
6 | Extension Reforms Monitoring System |  | Not Started | Not Started | No |  | Yes |  | No | No | No | Pending | Pending
7 | Plant Quarantine Information System (PQIS) |  | Not Started | Completed | No |  | Yes |  | No | No | No | Pending | Pending
8 | RKVY Application |  | Not Started | Not Started | No |  | Yes |  | No | No | No | Pending | Pending
9 | Seed Net |  | Not Started | Not Started | No |  | No |  | No | No | No | Pending | Pending
10 | Hortinet Traceability System |  |  | Not Started | No |  | No |  | No | No | No | Pending | Pending
11 | Soil Health Application |  | Completed | Completed | No |  | Yes | 21/03/2023 | Yes | No | No | Pending | Pending
12 | PM KISAN |  | Not Started | Completed | No |  | No | 21/03/2023 | No | No | No | Pending | Pending
13 | Horticulture Area and Production Statistics (HAPIS) |  | Not Started | Completed | No |  | NA | 21/03/2023 | NA | NA | NA | NA | NA
14 | Hortnet Application |  | Obselete | Completed | No |  | Yes |  | No | No | No | Pending | Pending
15 | National Agriculture Market (e-Nam) |  | Completed | Completed | In Progress |  | Yes | 24/04/2023 | No | No | No | Pending | Pending
16 | Agricultural Marketing Information Network (AGMARKNET) |  | Completed | Completed | In Progress |  | No | 24/04/2023 | No | No | No | Pending | Pending
17 | TraceNet |  | Not Started | Not Started | No |  | No |  | No | No | No | Pending | Pending