## Sheet1
Title | Function | SP/Table | API | UI
Audit Login/Register
Manage Role/Menu for audit
Masters pages(4 pages) | Add/Update/Delete/List | 8 Hours | 8 Hours | 5 Hours
Audit Authorization | Appove/Reject | 1 Hour | 2 Hour | 2 Hour | once auditor register, admin can approve/reject
Dashboard | Filter/View | 6 Hours | 4 Hours | 3 Hours
Common Dashboard | Filter/View | 6 Hours | 4 Hours | 3 Hours
Audit Schedule | Add/Submit | 4 Hours | 4 Hours | 2 Hours
Audit Activity Roadmap | Filter/View | 4 Hours | 4 Hours | 2 Hours
View Audit Schedule | View/List/Submit | 4 Hours | 4 Hours | 2 Hours
Audit Para | Add/List/Submit/Export/Document Upload | 8 Hours | 6 Hours | 3 Hours
Upload Audit Para | Upload | 8 Hours | 8 Hours | 1 Hours | need to manage Parent and Child table for upload functionality.
Audit Para Reassign | Reassign Submit | 4 Hours | 4 Hours | 1.5 Hours
Audit Para Clarification | Clarification Submit | 4 Hours | 4 Hours | 1.5 Hours
Audit Para Complience | Complience Submit | 4 Hours | 4 Hours | 1.5 Hours
Audit Information | View/submit/Filter | 4 Hours | 4 Hours | 3 Hours
Report-SMART | View/Filter | 4 Hours | 4 Hours | 3 Hours
Complience Certificate | Add/View/Upload/Edit/Delete/Export | 8 Hours | 6 Hours | 3 Hours